## Projects
Project_ID | Project_Name | Project_Type | Location | Project_Size | Total_Budget | Start_Date | End_Date | Duration_Months | Progress_Percent | Status | Project_Manager | General_Contractor | Architect | Client | Risk_Score | Quality_Score | Safety_Score | Environmental_Impact | Sustainability_Rating | Permits_Status | Last_Updated | Notes
PROJ001 | Downtown Office Tower | Commercial Office Building | 123 Business District, Metro City | 450,000 sq ft | 25000000 | 2024-01-18 | 2025-07-11 | 18 | 100 | Completed | PM Davis | Alpha Construction | Modern Design Group | Metro Industries | 3 | 9 | 9 | High | LEED Gold | Pending | 2025-09-19 12:36:21 | Major commercial office building project with innovative requirements
PROJ002 | Riverside Apartments | Residential Complex | 789 Riverside Drive, Metro City | 200 units | 18000000 | 2024-03-27 | 2025-05-21 | 14 | 100 | At Risk | PM Johnson | Delta Construction | Classic Design Group | United Corp | 8 | 6 | 10 | Medium | Green Building | Approved | 2025-09-19 12:36:21 | Major residential complex project with complex requirements
PROJ003 | Tech Campus Expansion | Commercial Office Building | 456 Innovation Park, Tech Valley | 600,000 sq ft | 35000000 | 2024-04-14 | 2026-04-04 | 24 | 72.6 | In Progress | PM Johnson | Beta Construction | Urban Design Group | Premier Industries | 7 | 9 | 10 | Medium | LEED Gold | Pending | 2025-09-19 12:36:21 | Major commercial office building project with innovative requirements
PROJ004 | Metro Hospital Wing | Healthcare Facility | 321 Medical Center Dr, Metro City | 300,000 sq ft | 45000000 | 2024-04-01 | 2026-09-18 | 30 | 59.6 | In Progress | PM Davis | Delta Construction | Modern Design Group | United Group | 2 | 6 | 7 | Medium | LEED Silver | Pending | 2025-09-19 12:36:21 | Major healthcare facility project with standard requirements
PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | 987 Industrial Blvd, Port District | 800,000 sq ft | 12000000 | 2024-01-28 | 2025-01-22 | 12 | 100 | At Risk | PM Davis | Gamma Construction | Green Design Group | Global Holdings | 9 | 7 | 9 | Low | LEED Platinum | Under Review | 2025-09-19 12:36:21 | Major industrial warehouse project with standard requirements
PROJ006 | University Science Center | Educational Institution | 654 Campus Way, University Town | 250,000 sq ft | 28000000 | 2024-03-24 | 2025-11-14 | 20 | 90.7 | Near Completion | PM Smith | Gamma Construction | Urban Design Group | Global Group | 6 | 6 | 7 | Low | LEED Silver | Pending | 2025-09-19 12:36:21 | Major educational institution project with standard requirements
PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | 147 Mall Road, Suburbia | 180,000 sq ft | 15000000 | 2024-01-28 | 2025-05-22 | 16 | 100 | Completed | PM Smith | Delta Construction | Classic Design Group | Metro Corp | 6 | 8 | 10 | Low | LEED Platinum | Approved | 2025-09-19 12:36:21 | Major retail shopping center project with innovative requirements

## Schedule
Task_ID | Project_ID | Project_Name | Project_Type | Phase | Task_Name | Start_Date | End_Date | Duration_Days | Progress_Percent | Status | Responsible_Team | Delay_Days | Delay_Reason | Priority | Dependencies | Critical_Path
T0001 | PROJ001 | Downtown Office Tower | Commercial Office Building | Pre-Construction | Pre-Construction - Downtown Office Tower | 2024-01-25 | 2024-02-16 | 22 | 100 | Completed | General Contractor | 0 |  | Low |  | FALSE
T0002 | PROJ001 | Downtown Office Tower | Commercial Office Building | Site Preparation | Site Preparation - Downtown Office Tower | 2024-02-17 | 2024-03-28 | 40 | 100 | Completed | Quality Control | 0 |  | Medium | T0001 | FALSE
T0003 | PROJ001 | Downtown Office Tower | Commercial Office Building | Foundation | Foundation - Downtown Office Tower | 2024-03-29 | 2024-06-06 | 69 | 100 | Completed | Structural | 0 |  | Low | T0002 | FALSE
T0004 | PROJ001 | Downtown Office Tower | Commercial Office Building | Structural | Structural - Downtown Office Tower | 2024-06-10 | 2024-10-11 | 123 | 100 | Completed | Quality Control | 0 |  | Medium | T0003 | FALSE
T0005 | PROJ001 | Downtown Office Tower | Commercial Office Building | MEP Systems | MEP Systems - Downtown Office Tower | 2024-10-13 | 2025-02-07 | 117 | 100 | Completed | Quality Control | 23 | Site conditions | High | T0004 | TRUE
T0006 | PROJ001 | Downtown Office Tower | Commercial Office Building | Interior Finishes | Interior Finishes - Downtown Office Tower | 2025-02-11 | 2025-05-27 | 105 | 100 | Completed | Finishes | 18 | Material shortages | High | T0005 | FALSE
T0007 | PROJ001 | Downtown Office Tower | Commercial Office Building | Exterior Finishes | Exterior Finishes - Downtown Office Tower | 2025-06-01 | 2025-07-10 | 39 | 100 | Completed | Quality Control | 0 |  | Medium | T0006 | FALSE
T0008 | PROJ001 | Downtown Office Tower | Commercial Office Building | Final Inspections | Final Inspections - Downtown Office Tower | 2025-07-15 | 2025-08-10 | 26 | 100 | Completed | MEP | 0 |  | Medium | T0007 | FALSE
T0009 | PROJ001 | Downtown Office Tower | Commercial Office Building | Project Closeout | Project Closeout - Downtown Office Tower | 2025-08-14 | 2025-08-29 | 15 | 100 | Completed | MEP | 5 | Equipment issues | Medium | T0008 | FALSE
T0010 | PROJ002 | Riverside Apartments | Residential Complex | Pre-Construction | Pre-Construction - Riverside Apartments | 2024-02-23 | 2024-03-30 | 36 | 100 | Completed | Finishes | 0 |  | High |  | FALSE
T0011 | PROJ002 | Riverside Apartments | Residential Complex | Site Preparation | Site Preparation - Riverside Apartments | 2024-03-31 | 2024-05-07 | 37 | 100 | Completed | MEP | 0 |  | Low | T0010 | FALSE
T0012 | PROJ002 | Riverside Apartments | Residential Complex | Foundation | Foundation - Riverside Apartments | 2024-05-12 | 2024-08-08 | 88 | 100 | Completed | Structural | 27 | Material shortages | Medium | T0011 | FALSE
T0013 | PROJ002 | Riverside Apartments | Residential Complex | Structural | Structural - Riverside Apartments | 2024-08-12 | 2024-12-16 | 126 | 100 | Completed | Quality Control | 0 |  | Low | T0012 | TRUE
T0014 | PROJ002 | Riverside Apartments | Residential Complex | MEP Systems | MEP Systems - Riverside Apartments | 2024-12-18 | 2025-03-11 | 83 | 100 | Completed | MEP | 0 |  | High | T0013 | FALSE
T0015 | PROJ002 | Riverside Apartments | Residential Complex | Interior Finishes | Interior Finishes - Riverside Apartments | 2025-03-12 | 2025-05-17 | 66 | 100 | Completed | Structural | 0 |  | High | T0014 | FALSE
T0016 | PROJ002 | Riverside Apartments | Residential Complex | Exterior Finishes | Exterior Finishes - Riverside Apartments | 2025-05-18 | 2025-07-21 | 64 | 100 | Completed | Structural | 0 |  | Low | T0015 | FALSE
T0017 | PROJ002 | Riverside Apartments | Residential Complex | Final Inspections | Final Inspections - Riverside Apartments | 2025-07-26 | 2025-08-04 | 9 | 100 | Completed | Structural | 0 |  | High | T0016 | FALSE
T0018 | PROJ002 | Riverside Apartments | Residential Complex | Project Closeout | Project Closeout - Riverside Apartments | 2025-08-08 | 2025-09-20 | 43 | 100 | Completed | Finishes | 24 | Equipment issues | High | T0017 | FALSE
T0019 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Pre-Construction | Pre-Construction - Tech Campus Expansion | 2024-03-28 | 2024-05-02 | 35 | 100 | Completed | Structural | 0 |  | High |  | FALSE
T0020 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Site Preparation | Site Preparation - Tech Campus Expansion | 2024-05-05 | 2024-07-05 | 61 | 100 | Completed | Structural | 0 |  | High | T0019 | FALSE
T0021 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Foundation | Foundation - Tech Campus Expansion | 2024-07-08 | 2024-09-06 | 60 | 100 | Completed | Finishes | 0 |  | High | T0020 | FALSE
T0022 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Structural | Structural - Tech Campus Expansion | 2024-09-10 | 2025-01-20 | 132 | 100 | Completed | Quality Control | 0 |  | Medium | T0021 | FALSE
T0023 | PROJ003 | Tech Campus Expansion | Commercial Office Building | MEP Systems | MEP Systems - Tech Campus Expansion | 2025-01-24 | 2025-05-19 | 115 | 100 | Completed | Quality Control | 20 | Supply chain disruptions | Medium | T0022 | TRUE
T0024 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Interior Finishes | Interior Finishes - Tech Campus Expansion | 2025-05-22 | 2025-08-06 | 76 | 100 | Completed | MEP | 0 |  | Medium | T0023 | FALSE
T0025 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Exterior Finishes | Exterior Finishes - Tech Campus Expansion | 2025-08-07 | 2025-09-24 | 48 | 81.6 | Near Completion | MEP | 0 |  | Medium | T0024 | FALSE
T0026 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Final Inspections | Final Inspections - Tech Campus Expansion | 2025-09-27 | 2025-11-08 | 42 | 0 | Not Started | Finishes | 8 | Supply chain disruptions | Low | T0025 | FALSE
T0027 | PROJ003 | Tech Campus Expansion | Commercial Office Building | Project Closeout | Project Closeout - Tech Campus Expansion | 2025-11-09 | 2025-11-21 | 12 | 0 | Not Started | Structural | 8 | Permit delays | Low | T0026 | FALSE
T0028 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Pre-Construction | Pre-Construction - Metro Hospital Wing | 2024-03-16 | 2024-05-05 | 50 | 100 | Completed | General Contractor | 0 |  | Medium |  | FALSE
T0029 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Site Preparation | Site Preparation - Metro Hospital Wing | 2024-05-07 | 2024-06-25 | 49 | 100 | Completed | Quality Control | 0 |  | Medium | T0028 | FALSE
T0030 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Foundation | Foundation - Metro Hospital Wing | 2024-06-29 | 2024-08-30 | 62 | 100 | Completed | Finishes | 0 |  | High | T0029 | FALSE
T0031 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Structural | Structural - Metro Hospital Wing | 2024-09-03 | 2025-01-12 | 131 | 100 | Completed | Quality Control | 21 | Supply chain disruptions | High | T0030 | TRUE
T0032 | PROJ004 | Metro Hospital Wing | Healthcare Facility | MEP Systems | MEP Systems - Metro Hospital Wing | 2025-01-13 | 2025-04-29 | 106 | 100 | Completed | Finishes | 0 |  | Medium | T0031 | FALSE
T0033 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Interior Finishes | Interior Finishes - Metro Hospital Wing | 2025-05-01 | 2025-07-30 | 90 | 100 | Completed | Quality Control | 0 |  | Medium | T0032 | FALSE
T0034 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Exterior Finishes | Exterior Finishes - Metro Hospital Wing | 2025-08-02 | 2025-09-06 | 35 | 100 | Completed | Quality Control | 0 |  | High | T0033 | FALSE
T0035 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Final Inspections | Final Inspections - Metro Hospital Wing | 2025-09-11 | 2025-09-28 | 17 | 42.1 | In Progress | Quality Control | 0 |  | High | T0034 | FALSE
T0036 | PROJ004 | Metro Hospital Wing | Healthcare Facility | Project Closeout | Project Closeout - Metro Hospital Wing | 2025-10-02 | 2025-11-26 | 55 | 0 | Not Started | MEP | 26 | Labor availability | Low | T0035 | FALSE
T0037 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Pre-Construction | Pre-Construction - Logistics Hub Warehouse | 2024-03-09 | 2024-04-04 | 26 | 100 | Completed | Structural | 0 |  | Low |  | FALSE
T0038 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Site Preparation | Site Preparation - Logistics Hub Warehouse | 2024-04-06 | 2024-05-25 | 49 | 100 | Completed | Finishes | 0 |  | Low | T0037 | FALSE
T0039 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Foundation | Foundation - Logistics Hub Warehouse | 2024-05-27 | 2024-08-15 | 80 | 100 | Completed | General Contractor | 0 |  | Low | T0038 | TRUE
T0040 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Structural | Structural - Logistics Hub Warehouse | 2024-08-17 | 2025-01-03 | 139 | 100 | Completed | MEP | 0 |  | Low | T0039 | TRUE
T0041 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | MEP Systems | MEP Systems - Logistics Hub Warehouse | 2025-01-05 | 2025-04-05 | 90 | 100 | Completed | General Contractor | 0 |  | High | T0040 | TRUE
T0042 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Interior Finishes | Interior Finishes - Logistics Hub Warehouse | 2025-04-06 | 2025-06-21 | 76 | 100 | Completed | Finishes | 0 |  | Low | T0041 | FALSE
T0043 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Exterior Finishes | Exterior Finishes - Logistics Hub Warehouse | 2025-06-24 | 2025-08-26 | 63 | 100 | Completed | MEP | 11 | Labor availability | Low | T0042 | FALSE
T0044 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Final Inspections | Final Inspections - Logistics Hub Warehouse | 2025-08-30 | 2025-09-27 | 28 | 79.4 | In Progress | Structural | 0 |  | High | T0043 | FALSE
T0045 | PROJ005 | Logistics Hub Warehouse | Industrial Warehouse | Project Closeout | Project Closeout - Logistics Hub Warehouse | 2025-09-28 | 2025-10-26 | 28 | 0 | Not Started | Structural | 0 |  | Low | T0044 | FALSE
T0046 | PROJ006 | University Science Center | Educational Institution | Pre-Construction | Pre-Construction - University Science Center | 2024-03-28 | 2024-04-30 | 33 | 100 | Completed | Quality Control | 0 |  | Low |  | FALSE
T0047 | PROJ006 | University Science Center | Educational Institution | Site Preparation | Site Preparation - University Science Center | 2024-05-02 | 2024-06-22 | 51 | 100 | Completed | MEP | 0 |  | High | T0046 | FALSE
T0048 | PROJ006 | University Science Center | Educational Institution | Foundation | Foundation - University Science Center | 2024-06-26 | 2024-08-28 | 63 | 100 | Completed | Finishes | 7 | Material shortages | Low | T0047 | TRUE
T0049 | PROJ006 | University Science Center | Educational Institution | Structural | Structural - University Science Center | 2024-08-30 | 2025-01-01 | 124 | 100 | Completed | Quality Control | 0 |  | Medium | T0048 | FALSE
T0050 | PROJ006 | University Science Center | Educational Institution | MEP Systems | MEP Systems - University Science Center | 2025-01-03 | 2025-04-30 | 117 | 100 | Completed | Quality Control | 15 | Labor availability | High | T0049 | FALSE
T0051 | PROJ006 | University Science Center | Educational Institution | Interior Finishes | Interior Finishes - University Science Center | 2025-05-04 | 2025-07-19 | 76 | 100 | Completed | Finishes | 0 |  | Medium | T0050 | FALSE
T0052 | PROJ006 | University Science Center | Educational Institution | Exterior Finishes | Exterior Finishes - University Science Center | 2025-07-21 | 2025-10-02 | 73 | 79.2 | Delayed | Structural | 8 | Supply chain disruptions | Low | T0051 | FALSE
T0053 | PROJ006 | University Science Center | Educational Institution | Final Inspections | Final Inspections - University Science Center | 2025-10-03 | 2025-10-10 | 7 | 0 | Not Started | General Contractor | 0 |  | High | T0052 | FALSE
T0054 | PROJ006 | University Science Center | Educational Institution | Project Closeout | Project Closeout - University Science Center | 2025-10-15 | 2025-11-06 | 22 | 0 | Not Started | Quality Control | 0 |  | Medium | T0053 | FALSE
T0055 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Pre-Construction | Pre-Construction - Suburban Shopping Plaza | 2024-03-07 | 2024-04-14 | 38 | 100 | Completed | MEP | 0 |  | Low |  | FALSE
T0056 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Site Preparation | Site Preparation - Suburban Shopping Plaza | 2024-04-17 | 2024-07-06 | 80 | 100 | Completed | Finishes | 16 | Supply chain disruptions | Medium | T0055 | FALSE
T0057 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Foundation | Foundation - Suburban Shopping Plaza | 2024-07-11 | 2024-09-09 | 60 | 100 | Completed | MEP | 0 |  | High | T0056 | FALSE
T0058 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Structural | Structural - Suburban Shopping Plaza | 2024-09-11 | 2025-01-02 | 113 | 100 | Completed | Quality Control | 0 |  | High | T0057 | TRUE
T0059 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | MEP Systems | MEP Systems - Suburban Shopping Plaza | 2025-01-04 | 2025-04-18 | 104 | 100 | Completed | Structural | 17 | Material shortages | Low | T0058 | FALSE
T0060 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Interior Finishes | Interior Finishes - Suburban Shopping Plaza | 2025-04-23 | 2025-07-05 | 73 | 100 | Completed | Structural | 0 |  | Low | T0059 | FALSE
T0061 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Exterior Finishes | Exterior Finishes - Suburban Shopping Plaza | 2025-07-07 | 2025-09-30 | 85 | 87.1 | Delayed | Finishes | 21 | Material shortages | Low | T0060 | FALSE
T0062 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Final Inspections | Final Inspections - Suburban Shopping Plaza | 2025-10-05 | 2025-11-09 | 35 | 0 | Not Started | Structural | 23 | Supply chain disruptions | Medium | T0061 | FALSE
T0063 | PROJ007 | Suburban Shopping Plaza | Retail Shopping Center | Project Closeout | Project Closeout - Suburban Shopping Plaza | 2025-11-13 | 2025-12-25 | 42 | 0 | Not Started | General Contractor | 30 | Site conditions | Low | T0062 | FALSE

## Budget_Tracking
Budget_ID | Project_ID | Project_Name | Cost_Category | Allocated_Budget | Actual_Spent | Remaining_Budget | Budget_Status | Variance_Percent | Last_Updated | Vendor | Purchase_Orders | Committed_Costs | Monthly_Spending | Risk_Level | Notes
B0001 | PROJ001 | Downtown Office Tower | Site Preparation | 2000000 | 1591116.57 | 408883.43 | Within Budget | -20.44 | 2025-09-19 | Site Preparation Contractor Inc. | 21 | 591990.45 | [{"month": "2024-01", "amount": 144368.7}, {"month": "2024-01", "amount": 218345.46}, {"month": "2024-03", "amount": 116696.12}, {"month": "2024-03", "amount": 236936.62}, {"month": "2024-04", "amount": 74835.99}, {"month": "2024-05", "amount": 171266.79}, {"month": "2024-06", "amount": 180954.98}, {"month": "2024-07", "amount": 125443.63}, {"month": "2024-08", "amount": 111272.84}, {"month": "2024-09", "amount": 199310.44}, {"month": "2024-10", "amount": 69996.8}, {"month": "2024-11", "amount": 128120.32}] | Low | Budget tracking for Site Preparation activities
B0002 | PROJ001 | Downtown Office Tower | Foundation | 3750000 | 1924910.4 | 1825089.6 | Within Budget | -48.67 | 2025-09-19 | Foundation Contractor Inc. | 15 | 544951.33 | [{"month": "2024-01", "amount": 240414.4}, {"month": "2024-01", "amount": 89276.84}, {"month": "2024-03", "amount": 261555.76}, {"month": "2024-03", "amount": 123695.96}, {"month": "2024-04", "amount": 117305.63}, {"month": "2024-05", "amount": 199545.82}, {"month": "2024-06", "amount": 235351.31}, {"month": "2024-07", "amount": 177912.03}, {"month": "2024-08", "amount": 216517.33}, {"month": "2024-09", "amount": 176026.05}, {"month": "2024-10", "amount": 218948.2}, {"month": "2024-11", "amount": 148560.66}] | Medium | Budget tracking for Foundation activities
B0003 | PROJ001 | Downtown Office Tower | Structural Steel | 5000000 | 2855017.68 | 2144982.32 | Within Budget | -42.9 | 2025-09-19 | Structural Steel Contractor Inc. | 12 | 1251950.63 | [{"month": "2024-01", "amount": 160908.88}, {"month": "2024-01", "amount": 190349.98}, {"month": "2024-03", "amount": 227365.32}, {"month": "2024-03", "amount": 397873.08}, {"month": "2024-04", "amount": 227476.63}, {"month": "2024-05", "amount": 135179.78}, {"month": "2024-06", "amount": 196993.63}, {"month": "2024-07", "amount": 392405.05}, {"month": "2024-08", "amount": 179496.92}, {"month": "2024-09", "amount": 367867.6}, {"month": "2024-10", "amount": 337351.29}, {"month": "2024-11", "amount": 302710.54}] | Low | Budget tracking for Structural Steel activities
B0004 | PROJ001 | Downtown Office Tower | Concrete | 3000000 | 1673817.25 | 1326182.75 | Within Budget | -44.21 | 2025-09-19 | Concrete Contractor Inc. | 9 | 606793.16 | [{"month": "2024-01", "amount": 82663.66}, {"month": "2024-01", "amount": 87529.45}, {"month": "2024-03", "amount": 156587.11}, {"month": "2024-03", "amount": 189853.91}, {"month": "2024-04", "amount": 110807.25}, {"month": "2024-05", "amount": 213692.07}, {"month": "2024-06", "amount": 102952.2}, {"month": "2024-07", "amount": 73272.99}, {"month": "2024-08", "amount": 93506.33}, {"month": "2024-09", "amount": 223704.7}, {"month": "2024-10", "amount": 249615.59}, {"month": "2024-11", "amount": 174903.42}] | High | Budget tracking for Concrete activities
B0005 | PROJ001 | Downtown Office Tower | MEP Systems | 6250000 | 4726457.86 | 1523542.14 | Within Budget | -24.38 | 2025-09-19 | MEP Systems Contractor Inc. | 14 | 634835.97 | [{"month": "2024-01", "amount": 560697.02}, {"month": "2024-01", "amount": 225868.56}, {"month": "2024-03", "amount": 703703.12}, {"month": "2024-03", "amount": 505651.06}, {"month": "2024-04", "amount": 389113.95}, {"month": "2024-05", "amount": 398641.51}, {"month": "2024-06", "amount": 259482.92}, {"month": "2024-07", "amount": 461552.55}, {"month": "2024-08", "amount": 199421.63}, {"month": "2024-09", "amount": 299646.94}, {"month": "2024-10", "amount": 604994.7}, {"month": "2024-11", "amount": 511969.63}] | Low | Budget tracking for MEP Systems activities
B0006 | PROJ001 | Downtown Office Tower | Interior Finishes | 3000000 | 2771152.17 | 228847.83 | Near Budget Limit | -7.63 | 2025-09-19 | Interior Finishes Contractor Inc. | 14 | 711443.72 | [{"month": "2024-01", "amount": 160897.17}, {"month": "2024-01", "amount": 220134.16}, {"month": "2024-03", "amount": 397917.43}, {"month": "2024-03", "amount": 354007.82}, {"month": "2024-04", "amount": 346959.16}, {"month": "2024-05", "amount": 118042.6}, {"month": "2024-06", "amount": 406340.16}, {"month": "2024-07", "amount": 133015.72}, {"month": "2024-08", "amount": 314246.36}, {"month": "2024-09", "amount": 129509.11}, {"month": "2024-10", "amount": 350210.44}, {"month": "2024-11", "amount": 284672.66}] | Medium | Budget tracking for Interior Finishes activities
B0007 | PROJ001 | Downtown Office Tower | Exterior Finishes | 1250000 | 570963.61 | 679036.39 | Within Budget | -54.32 | 2025-09-19 | Exterior Finishes Contractor Inc. | 14 | 189720.77 | [{"month": "2024-01", "amount": 25720.44}, {"month": "2024-01", "amount": 62708.94}, {"month": "2024-03", "amount": 61713.59}, {"month": "2024-03", "amount": 84839.66}, {"month": "2024-04", "amount": 77046.84}, {"month": "2024-05", "amount": 54436.51}, {"month": "2024-06", "amount": 50343.96}, {"month": "2024-07", "amount": 77342.93}, {"month": "2024-08", "amount": 56515.66}, {"month": "2024-09", "amount": 51204.08}, {"month": "2024-10", "amount": 74269.3}, {"month": "2024-11", "amount": 84070.87}] | Low | Budget tracking for Exterior Finishes activities
B0008 | PROJ001 | Downtown Office Tower | Equipment | 750000 | 681970.55 | 68029.45 | Near Budget Limit | -9.07 | 2025-09-19 | Equipment Contractor Inc. | 18 | 104770.18 | [{"month": "2024-01", "amount": 41449.76}, {"month": "2024-01", "amount": 83201.56}, {"month": "2024-03", "amount": 88697.04}, {"month": "2024-03", "amount": 74035.61}, {"month": "2024-04", "amount": 42175.23}, {"month": "2024-05", "amount": 31466.2}, {"month": "2024-06", "amount": 81813.7}, {"month": "2024-07", "amount": 44147.22}, {"month": "2024-08", "amount": 79040.51}, {"month": "2024-09", "amount": 67448.26}, {"month": "2024-10", "amount": 80176.98}, {"month": "2024-11", "amount": 77499.01}] | High | Budget tracking for Equipment activities
B0009 | PROJ002 | Riverside Apartments | Site Preparation | 1440000 | 478770.19 | 961229.81 | Within Budget | -66.75 | 2025-09-19 | Site Preparation Contractor Inc. | 19 | 215368.3 | [{"month": "2024-01", "amount": 66534.3}, {"month": "2024-01", "amount": 71746.98}, {"month": "2024-03", "amount": 60745.91}, {"month": "2024-03", "amount": 38600.57}, {"month": "2024-04", "amount": 70081.09}, {"month": "2024-05", "amount": 66822.07}, {"month": "2024-06", "amount": 39716.2}, {"month": "2024-07", "amount": 21795.67}, {"month": "2024-08", "amount": 27827.82}, {"month": "2024-09", "amount": 58179.6}, {"month": "2024-10", "amount": 38685.55}, {"month": "2024-11", "amount": 48525.77}] | Medium | Budget tracking for Site Preparation activities
B0010 | PROJ002 | Riverside Apartments | Foundation | 2700000 | 2177342.83 | 522657.17 | Within Budget | -19.36 | 2025-09-19 | Foundation Contractor Inc. | 23 | 276077.16 | [{"month": "2024-01", "amount": 173962.42}, {"month": "2024-01", "amount": 104375.57}, {"month": "2024-03", "amount": 259256.22}, {"month": "2024-03", "amount": 175034.42}, {"month": "2024-04", "amount": 161679.28}, {"month": "2024-05", "amount": 158850.3}, {"month": "2024-06", "amount": 166766.49}, {"month": "2024-07", "amount": 125459.12}, {"month": "2024-08", "amount": 236790.49}, {"month": "2024-09", "amount": 301643.52}, {"month": "2024-10", "amount": 288209.64}, {"month": "2024-11", "amount": 234390.42}] | Medium | Budget tracking for Foundation activities
B0011 | PROJ002 | Riverside Apartments | Structural Steel | 3600000 | 1673779.82 | 1926220.18 | Within Budget | -53.51 | 2025-09-19 | Structural Steel Contractor Inc. | 5 | 364503.54 | [{"month": "2024-01", "amount": 96214.31}, {"month": "2024-01", "amount": 90770.86}, {"month": "2024-03", "amount": 108492.74}, {"month": "2024-03", "amount": 139023.44}, {"month": "2024-04", "amount": 111749.26}, {"month": "2024-05", "amount": 170293.23}, {"month": "2024-06", "amount": 136266.04}, {"month": "2024-07", "amount": 110326.02}, {"month": "2024-08", "amount": 194550.51}, {"month": "2024-09", "amount": 158803.01}, {"month": "2024-10", "amount": 220851.9}, {"month": "2024-11", "amount": 93032.61}] | Medium | Budget tracking for Structural Steel activities
B0012 | PROJ002 | Riverside Apartments | Concrete | 2160000 | 1899154.57 | 260845.43 | Within Budget | -12.08 | 2025-09-19 | Concrete Contractor Inc. | 21 | 273014.67 | [{"month": "2024-01", "amount": 250904.94}, {"month": "2024-01", "amount": 219227.14}, {"month": "2024-03", "amount": 265137.8}, {"month": "2024-03", "amount": 278425.71}, {"month": "2024-04", "amount": 122891.08}, {"month": "2024-05", "amount": 277170.6}, {"month": "2024-06", "amount": 149303.85}, {"month": "2024-07", "amount": 207477.17}, {"month": "2024-08", "amount": 152271.12}, {"month": "2024-09", "amount": 208028.81}, {"month": "2024-10", "amount": 265710.82}, {"month": "2024-11", "amount": 244578.98}] | Medium | Budget tracking for Concrete activities
B0013 | PROJ002 | Riverside Apartments | MEP Systems | 4500000 | 1763774.26 | 2736225.74 | Within Budget | -60.81 | 2025-09-19 | MEP Systems Contractor Inc. | 21 | 1094019.31 | [{"month": "2024-01", "amount": 211500.16}, {"month": "2024-01", "amount": 239900.38}, {"month": "2024-03", "amount": 243109.82}, {"month": "2024-03", "amount": 234541.3}, {"month": "2024-04", "amount": 76529.23}, {"month": "2024-05", "amount": 90165.15}, {"month": "2024-06", "amount": 248733.21}, {"month": "2024-07", "amount": 203606.41}, {"month": "2024-08", "amount": 181066.05}, {"month": "2024-09", "amount": 181481.26}, {"month": "2024-10", "amount": 123446.69}, {"month": "2024-11", "amount": 227529.7}] | Medium | Budget tracking for MEP Systems activities
B0014 | PROJ002 | Riverside Apartments | Interior Finishes | 2160000 | 859365.35 | 1300634.65 | Within Budget | -60.21 | 2025-09-19 | Interior Finishes Contractor Inc. | 13 | 320636.46 | [{"month": "2024-01", "amount": 112696.05}, {"month": "2024-01", "amount": 109699.88}, {"month": "2024-03", "amount": 125408.27}, {"month": "2024-03", "amount": 126870.32}, {"month": "2024-04", "amount": 75541.62}, {"month": "2024-05", "amount": 55960.72}, {"month": "2024-06", "amount": 82145.09}, {"month": "2024-07", "amount": 113521.91}, {"month": "2024-08", "amount": 72887.18}, {"month": "2024-09", "amount": 95020.04}, {"month": "2024-10", "amount": 87904.24}, {"month": "2024-11", "amount": 80261.82}] | Medium | Budget tracking for Interior Finishes activities
B0015 | PROJ002 | Riverside Apartments | Exterior Finishes | 900000 | 437038.17 | 462961.83 | Within Budget | -51.44 | 2025-09-19 | Exterior Finishes Contractor Inc. | 22 | 123224.85 | [{"month": "2024-01", "amount": 65099.62}, {"month": "2024-01", "amount": 62032.14}, {"month": "2024-03", "amount": 29127.14}, {"month": "2024-03", "amount": 30023.03}, {"month": "2024-04", "amount": 62585.42}, {"month": "2024-05", "amount": 64481.01}, {"month": "2024-06", "amount": 23343.88}, {"month": "2024-07", "amount": 39003.36}, {"month": "2024-08", "amount": 61641.78}, {"month": "2024-09", "amount": 49673.51}, {"month": "2024-10", "amount": 26767.26}, {"month": "2024-11", "amount": 50491.6}] | Low | Budget tracking for Exterior Finishes activities
B0016 | PROJ002 | Riverside Apartments | Equipment | 540000 | 476495.24 | 63504.76 | Within Budget | -11.76 | 2025-09-19 | Equipment Contractor Inc. | 22 | 114095.09 | [{"month": "2024-01", "amount": 62266.38}, {"month": "2024-01", "amount": 51012.92}, {"month": "2024-03", "amount": 32767.87}, {"month": "2024-03", "amount": 52232.62}, {"month": "2024-04", "amount": 25506.59}, {"month": "2024-05", "amount": 48143.35}, {"month": "2024-06", "amount": 23032.23}, {"month": "2024-07", "amount": 65131.0}, {"month": "2024-08", "amount": 56826.23}, {"month": "2024-09", "amount": 46627.76}, {"month": "2024-10", "amount": 20573.27}, {"month": "2024-11", "amount": 36917.28}] | Low | Budget tracking for Equipment activities
B0017 | PROJ003 | Tech Campus Expansion | Site Preparation | 2800000 | 1301215.2 | 1498784.8 | Within Budget | -53.53 | 2025-09-19 | Site Preparation Contractor Inc. | 24 | 309237.03 | [{"month": "2024-01", "amount": 140595.51}, {"month": "2024-01", "amount": 158915.42}, {"month": "2024-03", "amount": 165767.18}, {"month": "2024-03", "amount": 119075.31}, {"month": "2024-04", "amount": 184355.03}, {"month": "2024-05", "amount": 105522.13}, {"month": "2024-06", "amount": 92778.67}, {"month": "2024-07", "amount": 187672.48}, {"month": "2024-08", "amount": 110190.16}, {"month": "2024-09", "amount": 122170.44}, {"month": "2024-10", "amount": 86918.14}, {"month": "2024-11", "amount": 194553.78}] | Medium | Budget tracking for Site Preparation activities
B0018 | PROJ003 | Tech Campus Expansion | Foundation | 5250000 | 4043422.07 | 1206577.93 | Within Budget | -22.98 | 2025-09-19 | Foundation Contractor Inc. | 8 | 777900.11 | [{"month": "2024-01", "amount": 570906.05}, {"month": "2024-01", "amount": 559590.1}, {"month": "2024-03", "amount": 517162.21}, {"month": "2024-03", "amount": 283875.09}, {"month": "2024-04", "amount": 444293.55}, {"month": "2024-05", "amount": 437277.11}, {"month": "2024-06", "amount": 433317.21}, {"month": "2024-07", "amount": 567425.08}, {"month": "2024-08", "amount": 298149.39}, {"month": "2024-09", "amount": 211180.32}, {"month": "2024-10", "amount": 311219.59}, {"month": "2024-11", "amount": 587853.11}] | Medium | Budget tracking for Foundation activities
B0019 | PROJ003 | Tech Campus Expansion | Structural Steel | 7000000 | 3854140.22 | 3145859.78 | Within Budget | -44.94 | 2025-09-19 | Structural Steel Contractor Inc. | 14 | 1345822.73 | [{"month": "2024-01", "amount": 197212.75}, {"month": "2024-01", "amount": 186423.49}, {"month": "2024-03", "amount": 287161.3}, {"month": "2024-03", "amount": 514046.08}, {"month": "2024-04", "amount": 276095.04}, {"month": "2024-05", "amount": 337246.38}, {"month": "2024-06", "amount": 357611.4}, {"month": "2024-07", "amount": 321442.79}, {"month": "2024-08", "amount": 536688.51}, {"month": "2024-09", "amount": 535985.65}, {"month": "2024-10", "amount": 402951.54}, {"month": "2024-11", "amount": 193991.13}] | High | Budget tracking for Structural Steel activities
B0020 | PROJ003 | Tech Campus Expansion | Concrete | 4200000 | 1491464.76 | 2708535.24 | Within Budget | -64.49 | 2025-09-19 | Concrete Contractor Inc. | 21 | 861818.52 | [{"month": "2024-01", "amount": 192678.0}, {"month": "2024-01", "amount": 99447.12}, {"month": "2024-03", "amount": 83227.95}, {"month": "2024-03", "amount": 111038.13}, {"month": "2024-04", "amount": 159872.0}, {"month": "2024-05", "amount": 78624.24}, {"month": "2024-06", "amount": 65743.69}, {"month": "2024-07", "amount": 137602.27}, {"month": "2024-08", "amount": 108262.69}, {"month": "2024-09", "amount": 82424.58}, {"month": "2024-10", "amount": 127415.43}, {"month": "2024-11", "amount": 121216.97}] | Low | Budget tracking for Concrete activities
B0021 | PROJ003 | Tech Campus Expansion | MEP Systems | 8750000 | 7711898.5 | 1038101.5 | Within Budget | -11.86 | 2025-09-19 | MEP Systems Contractor Inc. | 22 | 1335322.91 | [{"month": "2024-01", "amount": 643855.96}, {"month": "2024-01", "amount": 396171.89}, {"month": "2024-03", "amount": 535854.55}, {"month": "2024-03", "amount": 979652.14}, {"month": "2024-04", "amount": 437025.08}, {"month": "2024-05", "amount": 489669.5}, {"month": "2024-06", "amount": 1038737.74}, {"month": "2024-07", "amount": 968121.76}, {"month": "2024-08", "amount": 807108.04}, {"month": "2024-09", "amount": 614075.25}, {"month": "2024-10", "amount": 744885.14}, {"month": "2024-11", "amount": 497681.98}] | Medium | Budget tracking for MEP Systems activities
B0022 | PROJ003 | Tech Campus Expansion | Interior Finishes | 4200000 | 2332719.83 | 1867280.17 | Within Budget | -44.46 | 2025-09-19 | Interior Finishes Contractor Inc. | 16 | 778832.38 | [{"month": "2024-01", "amount": 295756.4}, {"month": "2024-01", "amount": 224911.97}, {"month": "2024-03", "amount": 178701.76}, {"month": "2024-03", "amount": 345210.14}, {"month": "2024-04", "amount": 347750.51}, {"month": "2024-05", "amount": 267680.05}, {"month": "2024-06", "amount": 278491.69}, {"month": "2024-07", "amount": 140959.63}, {"month": "2024-08", "amount": 310408.45}, {"month": "2024-09", "amount": 110197.9}, {"month": "2024-10", "amount": 308976.71}, {"month": "2024-11", "amount": 331135.92}] | Medium | Budget tracking for Interior Finishes activities
B0023 | PROJ003 | Tech Campus Expansion | Exterior Finishes | 1750000 | 947035.22 | 802964.78 | Within Budget | -45.88 | 2025-09-19 | Exterior Finishes Contractor Inc. | 10 | 523025.35 | [{"month": "2024-01", "amount": 103790.04}, {"month": "2024-01", "amount": 46121.55}, {"month": "2024-03", "amount": 96899.5}, {"month": "2024-03", "amount": 41160.5}, {"month": "2024-04", "amount": 41169.42}, {"month": "2024-05", "amount": 61761.33}, {"month": "2024-06", "amount": 105470.31}, {"month": "2024-07", "amount": 62116.12}, {"month": "2024-08", "amount": 72747.1}, {"month": "2024-09", "amount": 39654.57}, {"month": "2024-10", "amount": 91979.36}, {"month": "2024-11", "amount": 86728.09}] | Medium | Budget tracking for Exterior Finishes activities
B0024 | PROJ003 | Tech Campus Expansion | Equipment | 1050000 | 439055.94 | 610944.06 | Within Budget | -58.19 | 2025-09-19 | Equipment Contractor Inc. | 21 | 148557.06 | [{"month": "2024-01", "amount": 41837.72}, {"month": "2024-01", "amount": 42920.81}, {"month": "2024-03", "amount": 19141.09}, {"month": "2024-03", "amount": 28817.97}, {"month": "2024-04", "amount": 22733.83}, {"month": "2024-05", "amount": 53258.73}, {"month": "2024-06", "amount": 51227.27}, {"month": "2024-07", "amount": 34350.74}, {"month": "2024-08", "amount": 22770.47}, {"month": "2024-09", "amount": 43107.76}, {"month": "2024-10", "amount": 57828.44}, {"month": "2024-11", "amount": 46709.36}] | Low | Budget tracking for Equipment activities
B0025 | PROJ004 | Metro Hospital Wing | Site Preparation | 3600000 | 1960804.6 | 1639195.4 | Within Budget | -45.53 | 2025-09-19 | Site Preparation Contractor Inc. | 17 | 690156.15 | [{"month": "2024-01", "amount": 289487.76}, {"month": "2024-01", "amount": 155135.03}, {"month": "2024-03", "amount": 211933.29}, {"month": "2024-03", "amount": 293504.12}, {"month": "2024-04", "amount": 214046.46}, {"month": "2024-05", "amount": 135199.65}, {"month": "2024-06", "amount": 275062.52}, {"month": "2024-07", "amount": 208761.25}, {"month": "2024-08", "amount": 247544.3}, {"month": "2024-09", "amount": 263937.75}, {"month": "2024-10", "amount": 195140.34}, {"month": "2024-11", "amount": 151404.1}] | Low | Budget tracking for Site Preparation activities
B0026 | PROJ004 | Metro Hospital Wing | Foundation | 6750000 | 5182128.89 | 1567871.11 | Within Budget | -23.23 | 2025-09-19 | Foundation Contractor Inc. | 20 | 1488560.16 | [{"month": "2024-01", "amount": 399616.13}, {"month": "2024-01", "amount": 723571.39}, {"month": "2024-03", "amount": 256994.28}, {"month": "2024-03", "amount": 536742.78}, {"month": "2024-04", "amount": 749037.04}, {"month": "2024-05", "amount": 635992.95}, {"month": "2024-06", "amount": 575370.08}, {"month": "2024-07", "amount": 250671.78}, {"month": "2024-08", "amount": 259055.77}, {"month": "2024-09", "amount": 305474.28}, {"month": "2024-10", "amount": 397174.77}, {"month": "2024-11", "amount": 483161.51}] | Low | Budget tracking for Foundation activities
B0027 | PROJ004 | Metro Hospital Wing | Structural Steel | 9000000 | 4965799.34 | 4034200.66 | Within Budget | -44.82 | 2025-09-19 | Structural Steel Contractor Inc. | 9 | 1256346.24 | [{"month": "2024-01", "amount": 528904.61}, {"month": "2024-01", "amount": 254209.75}, {"month": "2024-03", "amount": 658199.72}, {"month": "2024-03", "amount": 314369.77}, {"month": "2024-04", "amount": 526031.98}, {"month": "2024-05", "amount": 652672.94}, {"month": "2024-06", "amount": 641019.51}, {"month": "2024-07", "amount": 520353.9}, {"month": "2024-08", "amount": 603175.24}, {"month": "2024-09", "amount": 539349.74}, {"month": "2024-10", "amount": 612083.19}, {"month": "2024-11", "amount": 283281.58}] | Low | Budget tracking for Structural Steel activities
B0028 | PROJ004 | Metro Hospital Wing | Concrete | 5400000 | 3882005.73 | 1517994.27 | Within Budget | -28.11 | 2025-09-19 | Concrete Contractor Inc. | 21 | 883733.38 | [{"month": "2024-01", "amount": 464145.34}, {"month": "2024-01", "amount": 555206.51}, {"month": "2024-03", "amount": 337165.19}, {"month": "2024-03", "amount": 335501.82}, {"month": "2024-04", "amount": 493815.21}, {"month": "2024-05", "amount": 480031.45}, {"month": "2024-06", "amount": 376866.14}, {"month": "2024-07", "amount": 189541.7}, {"month": "2024-08", "amount": 357541.55}, {"month": "2024-09", "amount": 482186.46}, {"month": "2024-10", "amount": 269291.79}, {"month": "2024-11", "amount": 419169.46}] | Medium | Budget tracking for Concrete activities
B0029 | PROJ004 | Metro Hospital Wing | MEP Systems | 11250000 | 6074879.14 | 5175120.86 | Within Budget | -46 | 2025-09-19 | MEP Systems Contractor Inc. | 15 | 1934756.94 | [{"month": "2024-01", "amount": 567356.95}, {"month": "2024-01", "amount": 456987.38}, {"month": "2024-03", "amount": 829722.12}, {"month": "2024-03", "amount": 332604.29}, {"month": "2024-04", "amount": 493832.92}, {"month": "2024-05", "amount": 686634.15}, {"month": "2024-06", "amount": 791238.59}, {"month": "2024-07", "amount": 440554.32}, {"month": "2024-08", "amount": 615342.65}, {"month": "2024-09", "amount": 270279.93}, {"month": "2024-10", "amount": 756154.03}, {"month": "2024-11", "amount": 560752.33}] | High | Budget tracking for MEP Systems activities
B0030 | PROJ004 | Metro Hospital Wing | Interior Finishes | 5400000 | 2697311.55 | 2702688.45 | Within Budget | -50.05 | 2025-09-19 | Interior Finishes Contractor Inc. | 5 | 1438810.59 | [{"month": "2024-01", "amount": 270535.68}, {"month": "2024-01", "amount": 395185.84}, {"month": "2024-03", "amount": 148611.68}, {"month": "2024-03", "amount": 254439.84}, {"month": "2024-04", "amount": 132131.1}, {"month": "2024-05", "amount": 289588.7}, {"month": "2024-06", "amount": 216085.94}, {"month": "2024-07", "amount": 263755.24}, {"month": "2024-08", "amount": 216397.95}, {"month": "2024-09", "amount": 396070.83}, {"month": "2024-10", "amount": 307937.21}, {"month": "2024-11", "amount": 196703.6}] | Medium | Budget tracking for Interior Finishes activities
B0031 | PROJ004 | Metro Hospital Wing | Exterior Finishes | 2250000 | 2192338.24 | 57661.76 | Near Budget Limit | -2.56 | 2025-09-19 | Exterior Finishes Contractor Inc. | 8 | 576184.68 | [{"month": "2024-01", "amount": 273632.18}, {"month": "2024-01", "amount": 109691.1}, {"month": "2024-03", "amount": 124733.43}, {"month": "2024-03", "amount": 92365.58}, {"month": "2024-04", "amount": 215916.79}, {"month": "2024-05", "amount": 284030.41}, {"month": "2024-06", "amount": 198293.39}, {"month": "2024-07", "amount": 152486.21}, {"month": "2024-08", "amount": 129411.8}, {"month": "2024-09", "amount": 119072.05}, {"month": "2024-10", "amount": 310269.64}, {"month": "2024-11", "amount": 148915.47}] | Medium | Budget tracking for Exterior Finishes activities
B0032 | PROJ004 | Metro Hospital Wing | Equipment | 1350000 | 1361596.08 | -11596.08 | Over Budget | 0.86 | 2025-09-19 | Equipment Contractor Inc. | 24 | 188518.39 | [{"month": "2024-01", "amount": 186895.43}, {"month": "2024-01", "amount": 78495.87}, {"month": "2024-03", "amount": 66543.14}, {"month": "2024-03", "amount": 116747.54}, {"month": "2024-04", "amount": 151907.29}, {"month": "2024-05", "amount": 141891.48}, {"month": "2024-06", "amount": 164377.58}, {"month": "2024-07", "amount": 101856.65}, {"month": "2024-08", "amount": 123666.47}, {"month": "2024-09", "amount": 115068.66}, {"month": "2024-10", "amount": 164374.9}, {"month": "2024-11", "amount": 135849.97}] | Low | Budget tracking for Equipment activities
B0033 | PROJ005 | Logistics Hub Warehouse | Site Preparation | 960000 | 424751.75 | 535248.25 | Within Budget | -55.76 | 2025-09-19 | Site Preparation Contractor Inc. | 7 | 126804.86 | [{"month": "2024-01", "amount": 38360.58}, {"month": "2024-01", "amount": 48171.75}, {"month": "2024-03", "amount": 30137.04}, {"month": "2024-03", "amount": 33828.44}, {"month": "2024-04", "amount": 27153.0}, {"month": "2024-05", "amount": 56403.19}, {"month": "2024-06", "amount": 35366.9}, {"month": "2024-07", "amount": 25164.37}, {"month": "2024-08", "amount": 52257.9}, {"month": "2024-09", "amount": 30235.55}, {"month": "2024-10", "amount": 54333.5}, {"month": "2024-11", "amount": 35946.63}] | Low | Budget tracking for Site Preparation activities
B0034 | PROJ005 | Logistics Hub Warehouse | Foundation | 1800000 | 1323214.13 | 476785.87 | Within Budget | -26.49 | 2025-09-19 | Foundation Contractor Inc. | 22 | 470509.04 | [{"month": "2024-01", "amount": 123766.83}, {"month": "2024-01", "amount": 84714.64}, {"month": "2024-03", "amount": 69597.59}, {"month": "2024-03", "amount": 91851.55}, {"month": "2024-04", "amount": 149369.84}, {"month": "2024-05", "amount": 188697.49}, {"month": "2024-06", "amount": 192239.2}, {"month": "2024-07", "amount": 178299.55}, {"month": "2024-08", "amount": 61942.71}, {"month": "2024-09", "amount": 167129.19}, {"month": "2024-10", "amount": 65907.61}, {"month": "2024-11", "amount": 194522.9}] | Low | Budget tracking for Foundation activities
B0035 | PROJ005 | Logistics Hub Warehouse | Structural Steel | 2400000 | 2232130.25 | 167869.75 | Near Budget Limit | -6.99 | 2025-09-19 | Structural Steel Contractor Inc. | 20 | 252564.79 | [{"month": "2024-01", "amount": 293592.79}, {"month": "2024-01", "amount": 305189.56}, {"month": "2024-03", "amount": 122299.48}, {"month": "2024-03", "amount": 108803.85}, {"month": "2024-04", "amount": 250819.4}, {"month": "2024-05", "amount": 147148.61}, {"month": "2024-06", "amount": 132851.82}, {"month": "2024-07", "amount": 189046.48}, {"month": "2024-08", "amount": 209330.09}, {"month": "2024-09", "amount": 219586.89}, {"month": "2024-10", "amount": 232464.76}, {"month": "2024-11", "amount": 295960.97}] | Low | Budget tracking for Structural Steel activities
B0036 | PROJ005 | Logistics Hub Warehouse | Concrete | 1440000 | 1160455.16 | 279544.84 | Within Budget | -19.41 | 2025-09-19 | Concrete Contractor Inc. | 23 | 392366.87 | [{"month": "2024-01", "amount": 134911.56}, {"month": "2024-01", "amount": 69811.07}, {"month": "2024-03", "amount": 49275.59}, {"month": "2024-03", "amount": 83709.24}, {"month": "2024-04", "amount": 119446.69}, {"month": "2024-05", "amount": 151054.42}, {"month": "2024-06", "amount": 111530.52}, {"month": "2024-07", "amount": 167460.01}, {"month": "2024-08", "amount": 82541.72}, {"month": "2024-09", "amount": 80576.58}, {"month": "2024-10", "amount": 134261.66}, {"month": "2024-11", "amount": 129239.38}] | Medium | Budget tracking for Concrete activities
B0037 | PROJ005 | Logistics Hub Warehouse | MEP Systems | 3000000 | 2991222.77 | 8777.23 | Near Budget Limit | -0.29 | 2025-09-19 | MEP Systems Contractor Inc. | 12 | 410257.32 | [{"month": "2024-01", "amount": 252731.46}, {"month": "2024-01", "amount": 317164.68}, {"month": "2024-03", "amount": 170320.84}, {"month": "2024-03", "amount": 361982.01}, {"month": "2024-04", "amount": 163123.92}, {"month": "2024-05", "amount": 308463.09}, {"month": "2024-06", "amount": 330361.46}, {"month": "2024-07", "amount": 422607.39}, {"month": "2024-08", "amount": 175365.76}, {"month": "2024-09", "amount": 336799.4}, {"month": "2024-10", "amount": 258920.72}, {"month": "2024-11", "amount": 419075.31}] | Medium | Budget tracking for MEP Systems activities
B0038 | PROJ005 | Logistics Hub Warehouse | Interior Finishes | 1440000 | 1067301.76 | 372698.24 | Within Budget | -25.88 | 2025-09-19 | Interior Finishes Contractor Inc. | 11 | 413267.27 | [{"month": "2024-01", "amount": 49958.74}, {"month": "2024-01", "amount": 50052.19}, {"month": "2024-03", "amount": 130841.88}, {"month": "2024-03", "amount": 68479.17}, {"month": "2024-04", "amount": 116552.85}, {"month": "2024-05", "amount": 104393.87}, {"month": "2024-06", "amount": 81705.08}, {"month": "2024-07", "amount": 51791.21}, {"month": "2024-08", "amount": 108077.82}, {"month": "2024-09", "amount": 137411.3}, {"month": "2024-10", "amount": 82765.42}, {"month": "2024-11", "amount": 116638.79}] | Medium | Budget tracking for Interior Finishes activities
B0039 | PROJ005 | Logistics Hub Warehouse | Exterior Finishes | 600000 | 429320.81 | 170679.19 | Within Budget | -28.45 | 2025-09-19 | Exterior Finishes Contractor Inc. | 11 | 90493.49 | [{"month": "2024-01", "amount": 32582.42}, {"month": "2024-01", "amount": 51232.47}, {"month": "2024-03", "amount": 43642.8}, {"month": "2024-03", "amount": 30135.49}, {"month": "2024-04", "amount": 28875.67}, {"month": "2024-05", "amount": 44339.85}, {"month": "2024-06", "amount": 38304.24}, {"month": "2024-07", "amount": 52745.49}, {"month": "2024-08", "amount": 42372.98}, {"month": "2024-09", "amount": 43124.58}, {"month": "2024-10", "amount": 50601.36}, {"month": "2024-11", "amount": 33581.86}] | High | Budget tracking for Exterior Finishes activities
B0040 | PROJ005 | Logistics Hub Warehouse | Equipment | 360000 | 213346.21 | 146653.79 | Within Budget | -40.74 | 2025-09-19 | Equipment Contractor Inc. | 16 | 50940.77 | [{"month": "2024-01", "amount": 23364.8}, {"month": "2024-01", "amount": 22744.67}, {"month": "2024-03", "amount": 27036.17}, {"month": "2024-03", "amount": 29258.99}, {"month": "2024-04", "amount": 18143.6}, {"month": "2024-05", "amount": 22723.84}, {"month": "2024-06", "amount": 13523.8}, {"month": "2024-07", "amount": 14215.88}, {"month": "2024-08", "amount": 12490.04}, {"month": "2024-09", "amount": 13047.95}, {"month": "2024-10", "amount": 22918.77}, {"month": "2024-11", "amount": 15480.5}] | High | Budget tracking for Equipment activities
B0041 | PROJ006 | University Science Center | Site Preparation | 2240000 | 1733816.51 | 506183.49 | Within Budget | -22.6 | 2025-09-19 | Site Preparation Contractor Inc. | 13 | 562893.2 | [{"month": "2024-01", "amount": 247887.02}, {"month": "2024-01", "amount": 169905.13}, {"month": "2024-03", "amount": 243776.82}, {"month": "2024-03", "amount": 108338.45}, {"month": "2024-04", "amount": 166344.83}, {"month": "2024-05", "amount": 194208.18}, {"month": "2024-06", "amount": 124363.02}, {"month": "2024-07", "amount": 166563.81}, {"month": "2024-08", "amount": 81924.04}, {"month": "2024-09", "amount": 260033.34}, {"month": "2024-10", "amount": 91926.77}, {"month": "2024-11", "amount": 150270.95}] | Medium | Budget tracking for Site Preparation activities
B0042 | PROJ006 | University Science Center | Foundation | 4200000 | 3014812.86 | 1185187.14 | Within Budget | -28.22 | 2025-09-19 | Foundation Contractor Inc. | 13 | 1138451.46 | [{"month": "2024-01", "amount": 445535.77}, {"month": "2024-01", "amount": 272923.02}, {"month": "2024-03", "amount": 241961.8}, {"month": "2024-03", "amount": 290888.84}, {"month": "2024-04", "amount": 192615.79}, {"month": "2024-05", "amount": 345317.54}, {"month": "2024-06", "amount": 196668.51}, {"month": "2024-07", "amount": 345995.6}, {"month": "2024-08", "amount": 425992.25}, {"month": "2024-09", "amount": 129628.07}, {"month": "2024-10", "amount": 191833.11}, {"month": "2024-11", "amount": 130116.35}] | High | Budget tracking for Foundation activities
B0043 | PROJ006 | University Science Center | Structural Steel | 5600000 | 5104273.81 | 495726.19 | Near Budget Limit | -8.85 | 2025-09-19 | Structural Steel Contractor Inc. | 23 | 1062553.35 | [{"month": "2024-01", "amount": 564412.49}, {"month": "2024-01", "amount": 373891.79}, {"month": "2024-03", "amount": 240878.5}, {"month": "2024-03", "amount": 220003.45}, {"month": "2024-04", "amount": 610149.3}, {"month": "2024-05", "amount": 318299.32}, {"month": "2024-06", "amount": 419176.45}, {"month": "2024-07", "amount": 688959.53}, {"month": "2024-08", "amount": 467604.3}, {"month": "2024-09", "amount": 748250.5}, {"month": "2024-10", "amount": 386054.3}, {"month": "2024-11", "amount": 299397.72}] | Medium | Budget tracking for Structural Steel activities
B0044 | PROJ006 | University Science Center | Concrete | 3360000 | 3334699.18 | 25300.82 | Near Budget Limit | -0.75 | 2025-09-19 | Concrete Contractor Inc. | 17 | 744125.34 | [{"month": "2024-01", "amount": 477605.62}, {"month": "2024-01", "amount": 276772.47}, {"month": "2024-03", "amount": 337328.91}, {"month": "2024-03", "amount": 323596.81}, {"month": "2024-04", "amount": 398742.2}, {"month": "2024-05", "amount": 223528.87}, {"month": "2024-06", "amount": 322205.06}, {"month": "2024-07", "amount": 275015.16}, {"month": "2024-08", "amount": 298775.6}, {"month": "2024-09", "amount": 159937.84}, {"month": "2024-10", "amount": 322676.35}, {"month": "2024-11", "amount": 499317.14}] | Medium | Budget tracking for Concrete activities
B0045 | PROJ006 | University Science Center | MEP Systems | 7000000 | 2840702.02 | 4159297.98 | Within Budget | -59.42 | 2025-09-19 | MEP Systems Contractor Inc. | 19 | 1772938.7 | [{"month": "2024-01", "amount": 383521.07}, {"month": "2024-01", "amount": 242307.21}, {"month": "2024-03", "amount": 367633.09}, {"month": "2024-03", "amount": 313405.66}, {"month": "2024-04", "amount": 142703.8}, {"month": "2024-05", "amount": 191938.14}, {"month": "2024-06", "amount": 311208.52}, {"month": "2024-07", "amount": 320746.68}, {"month": "2024-08", "amount": 371170.37}, {"month": "2024-09", "amount": 118547.91}, {"month": "2024-10", "amount": 267852.43}, {"month": "2024-11", "amount": 402444.54}] | Medium | Budget tracking for MEP Systems activities
B0046 | PROJ006 | University Science Center | Interior Finishes | 3360000 | 2837296.06 | 522703.94 | Within Budget | -15.56 | 2025-09-19 | Interior Finishes Contractor Inc. | 21 | 856582.61 | [{"month": "2024-01", "amount": 276950.5}, {"month": "2024-01", "amount": 277960.35}, {"month": "2024-03", "amount": 217588.35}, {"month": "2024-03", "amount": 124642.53}, {"month": "2024-04", "amount": 141986.78}, {"month": "2024-05", "amount": 290182.31}, {"month": "2024-06", "amount": 211932.64}, {"month": "2024-07", "amount": 123623.09}, {"month": "2024-08", "amount": 171377.99}, {"month": "2024-09", "amount": 250186.05}, {"month": "2024-10", "amount": 399286.76}, {"month": "2024-11", "amount": 408968.08}] | Medium | Budget tracking for Interior Finishes activities
B0047 | PROJ006 | University Science Center | Exterior Finishes | 1400000 | 517370.92 | 882629.08 | Within Budget | -63.04 | 2025-09-19 | Exterior Finishes Contractor Inc. | 10 | 220735.49 | [{"month": "2024-01", "amount": 66837.53}, {"month": "2024-01", "amount": 57417.81}, {"month": "2024-03", "amount": 64792.66}, {"month": "2024-03", "amount": 66697.61}, {"month": "2024-04", "amount": 49597.6}, {"month": "2024-05", "amount": 33184.71}, {"month": "2024-06", "amount": 40257.43}, {"month": "2024-07", "amount": 66794.45}, {"month": "2024-08", "amount": 40387.36}, {"month": "2024-09", "amount": 42212.65}, {"month": "2024-10", "amount": 60359.48}, {"month": "2024-11", "amount": 65911.33}] | Medium | Budget tracking for Exterior Finishes activities
B0048 | PROJ006 | University Science Center | Equipment | 840000 | 648952.19 | 191047.81 | Within Budget | -22.74 | 2025-09-19 | Equipment Contractor Inc. | 12 | 195735.44 | [{"month": "2024-01", "amount": 83504.27}, {"month": "2024-01", "amount": 77367.67}, {"month": "2024-03", "amount": 44142.09}, {"month": "2024-03", "amount": 77723.01}, {"month": "2024-04", "amount": 81095.08}, {"month": "2024-05", "amount": 44515.53}, {"month": "2024-06", "amount": 36490.47}, {"month": "2024-07", "amount": 68507.95}, {"month": "2024-08", "amount": 77768.38}, {"month": "2024-09", "amount": 40460.06}, {"month": "2024-10", "amount": 66218.34}, {"month": "2024-11", "amount": 29090.73}] | High | Budget tracking for Equipment activities
B0049 | PROJ007 | Suburban Shopping Plaza | Site Preparation | 1200000 | 607984.85 | 592015.15 | Within Budget | -49.33 | 2025-09-19 | Site Preparation Contractor Inc. | 24 | 137567.62 | [{"month": "2024-01", "amount": 51464.67}, {"month": "2024-01", "amount": 88803.7}, {"month": "2024-03", "amount": 57364.15}, {"month": "2024-03", "amount": 60704.69}, {"month": "2024-04", "amount": 86738.57}, {"month": "2024-05", "amount": 56994.61}, {"month": "2024-06", "amount": 49074.63}, {"month": "2024-07", "amount": 40017.56}, {"month": "2024-08", "amount": 56359.47}, {"month": "2024-09", "amount": 71003.62}, {"month": "2024-10", "amount": 86920.07}, {"month": "2024-11", "amount": 55926.83}] | Low | Budget tracking for Site Preparation activities
B0050 | PROJ007 | Suburban Shopping Plaza | Foundation | 2250000 | 1174207.36 | 1075792.64 | Within Budget | -47.81 | 2025-09-19 | Foundation Contractor Inc. | 8 | 624742.38 | [{"month": "2024-01", "amount": 124053.7}, {"month": "2024-01", "amount": 148617.17}, {"month": "2024-03", "amount": 125739.25}, {"month": "2024-03", "amount": 64868.51}, {"month": "2024-04", "amount": 115357.78}, {"month": "2024-05", "amount": 128837.4}, {"month": "2024-06", "amount": 64556.71}, {"month": "2024-07", "amount": 60207.41}, {"month": "2024-08", "amount": 59299.61}, {"month": "2024-09", "amount": 99418.96}, {"month": "2024-10", "amount": 159415.56}, {"month": "2024-11", "amount": 117629.02}] | Medium | Budget tracking for Foundation activities
B0051 | PROJ007 | Suburban Shopping Plaza | Structural Steel | 3000000 | 1024570.96 | 1975429.04 | Within Budget | -65.85 | 2025-09-19 | Structural Steel Contractor Inc. | 21 | 333301.26 | [{"month": "2024-01", "amount": 102412.67}, {"month": "2024-01", "amount": 80234.17}, {"month": "2024-03", "amount": 84798.85}, {"month": "2024-03", "amount": 70794.54}, {"month": "2024-04", "amount": 61022.13}, {"month": "2024-05", "amount": 152468.03}, {"month": "2024-06", "amount": 65110.51}, {"month": "2024-07", "amount": 106969.57}, {"month": "2024-08", "amount": 115592.84}, {"month": "2024-09", "amount": 60163.86}, {"month": "2024-10", "amount": 141628.58}, {"month": "2024-11", "amount": 47802.49}] | Medium | Budget tracking for Structural Steel activities
B0052 | PROJ007 | Suburban Shopping Plaza | Concrete | 1800000 | 1474908.82 | 325091.18 | Within Budget | -18.06 | 2025-09-19 | Concrete Contractor Inc. | 15 | 224598.03 | [{"month": "2024-01", "amount": 198606.58}, {"month": "2024-01", "amount": 125959.4}, {"month": "2024-03", "amount": 192995.81}, {"month": "2024-03", "amount": 184953.4}, {"month": "2024-04", "amount": 129699.94}, {"month": "2024-05", "amount": 107441.97}, {"month": "2024-06", "amount": 131774.58}, {"month": "2024-07", "amount": 120928.18}, {"month": "2024-08", "amount": 152873.39}, {"month": "2024-09", "amount": 179762.22}, {"month": "2024-10", "amount": 119394.85}, {"month": "2024-11", "amount": 103522.06}] | Low | Budget tracking for Concrete activities
B0053 | PROJ007 | Suburban Shopping Plaza | MEP Systems | 3750000 | 1187094.89 | 2562905.11 | Within Budget | -68.34 | 2025-09-19 | MEP Systems Contractor Inc. | 14 | 1066073.78 | [{"month": "2024-01", "amount": 121236.79}, {"month": "2024-01", "amount": 99093.7}, {"month": "2024-03", "amount": 114036.74}, {"month": "2024-03", "amount": 169009.33}, {"month": "2024-04", "amount": 73945.29}, {"month": "2024-05", "amount": 142901.51}, {"month": "2024-06", "amount": 56337.4}, {"month": "2024-07", "amount": 94811.81}, {"month": "2024-08", "amount": 57873.25}, {"month": "2024-09", "amount": 74537.47}, {"month": "2024-10", "amount": 162926.79}, {"month": "2024-11", "amount": 60606.3}] | Medium | Budget tracking for MEP Systems activities
B0054 | PROJ007 | Suburban Shopping Plaza | Interior Finishes | 1800000 | 1501285.48 | 298714.52 | Within Budget | -16.6 | 2025-09-19 | Interior Finishes Contractor Inc. | 16 | 488184.35 | [{"month": "2024-01", "amount": 142477.84}, {"month": "2024-01", "amount": 80493.01}, {"month": "2024-03", "amount": 155511.68}, {"month": "2024-03", "amount": 210157.77}, {"month": "2024-04", "amount": 166867.56}, {"month": "2024-05", "amount": 117513.98}, {"month": "2024-06", "amount": 110969.09}, {"month": "2024-07", "amount": 189879.68}, {"month": "2024-08", "amount": 182892.46}, {"month": "2024-09", "amount": 182132.04}, {"month": "2024-10", "amount": 113069.53}, {"month": "2024-11", "amount": 162605.96}] | Medium | Budget tracking for Interior Finishes activities
B0055 | PROJ007 | Suburban Shopping Plaza | Exterior Finishes | 750000 | 594991.3 | 155008.7 | Within Budget | -20.67 | 2025-09-19 | Exterior Finishes Contractor Inc. | 24 | 93524.43 | [{"month": "2024-01", "amount": 58677.56}, {"month": "2024-01", "amount": 65998.76}, {"month": "2024-03", "amount": 48972.13}, {"month": "2024-03", "amount": 64200.54}, {"month": "2024-04", "amount": 37050.96}, {"month": "2024-05", "amount": 74795.26}, {"month": "2024-06", "amount": 69504.11}, {"month": "2024-07", "amount": 37684.41}, {"month": "2024-08", "amount": 58079.05}, {"month": "2024-09", "amount": 88244.64}, {"month": "2024-10", "amount": 66817.24}, {"month": "2024-11", "amount": 26653.8}] | Low | Budget tracking for Exterior Finishes activities
B0056 | PROJ007 | Suburban Shopping Plaza | Equipment | 450000 | 193048.28 | 256951.72 | Within Budget | -57.1 | 2025-09-19 | Equipment Contractor Inc. | 9 | 103219.26 | [{"month": "2024-01", "amount": 27648.31}, {"month": "2024-01", "amount": 20492.59}, {"month": "2024-03", "amount": 17182.24}, {"month": "2024-03", "amount": 12262.33}, {"month": "2024-04", "amount": 10946.12}, {"month": "2024-05", "amount": 28143.29}, {"month": "2024-06", "amount": 12039.59}, {"month": "2024-07", "amount": 22643.59}, {"month": "2024-08", "amount": 25945.68}, {"month": "2024-09", "amount": 25130.58}, {"month": "2024-10", "amount": 12925.73}, {"month": "2024-11", "amount": 25857.34}] | Low | Budget tracking for Equipment activities

## Resources
Resource_ID | Project_ID | Resource_Type | Resource_Name | Hourly_Rate | Allocated_Hours_Weekly | Utilized_Hours_Weekly | Efficiency_Percent | Allocated_Cost_Weekly | Actual_Cost_Weekly | Start_Date | End_Date | Availability_Status | Skill_Level | Certification_Status | Performance_Rating | Notes
R0001 | PROJ001 | Project Manager | Project Manager - Team A | 150 | 37 | 26.1 | 70.5 | 5549.63 | 4060.45 | 2025-08-19 | 2025-11-23 | Overallocated | Junior | Current | 10 | Resource allocation for Project Manager on project PROJ001
R0002 | PROJ001 | Site Supervisor | Site Supervisor - Team A | 120 | 28.4 | 21.4 | 75.2 | 3409.26 | 2565.57 | 2025-07-14 | 2025-12-16 | Available | Senior | Expiring Soon | 9 | Resource allocation for Site Supervisor on project PROJ001
R0003 | PROJ001 | Structural Engineer | Structural Engineer - Team B | 140 | 17.3 | 13.2 | 76.3 | 2426.65 | 1951.23 | 2025-08-01 | 2025-12-13 | Overallocated | Mid-Level | Current | 8 | Resource allocation for Structural Engineer on project PROJ001
R0004 | PROJ001 | MEP Engineer | MEP Engineer - Team A | 130 | 32.1 | 26.1 | 81.2 | 4169.03 | 3700.08 | 2025-08-02 | 2025-11-23 | Available | Junior | Expiring Soon | 8 | Resource allocation for MEP Engineer on project PROJ001
R0005 | PROJ001 | General Labor | General Labor - Team C | 35 | 314.9 | 258.2 | 82 | 11022.26 | 9759.9 | 2025-07-07 | 2026-01-20 | Partially Available | Mid-Level | Expiring Soon | 8 | Resource allocation for General Labor on project PROJ001
R0006 | PROJ001 | Skilled Carpenter | Skilled Carpenter - Team C | 45 | 132.3 | 93.6 | 70.7 | 5954.21 | 4523.37 | 2025-06-23 | 2025-12-05 | Available | Senior | Expiring Soon | 10 | Resource allocation for Skilled Carpenter on project PROJ001
R0007 | PROJ001 | Electrician | Electrician - Team A | 55 | 128.9 | 114.7 | 89 | 7090.3 | 6787.9 | 2025-04-11 | 2025-12-01 | Partially Available | Junior | Expiring Soon | 7 | Resource allocation for Electrician on project PROJ001
R0008 | PROJ001 | Plumber | Plumber - Team B | 50 | 69.2 | 51.1 | 73.9 | 3457.54 | 2588.52 | 2025-05-19 | 2026-01-15 | Partially Available | Junior | Expired | 7 | Resource allocation for Plumber on project PROJ001
R0009 | PROJ001 | Heavy Equipment Operator | Heavy Equipment Operator - Team B | 60 | 89.2 | 67 | 75.1 | 5350.84 | 4016.83 | 2025-05-09 | 2025-12-15 | Overallocated | Senior | Current | 9 | Resource allocation for Heavy Equipment Operator on project PROJ001
R0010 | PROJ001 | Safety Inspector | Safety Inspector - Team B | 80 | 17.3 | 12.9 | 74.4 | 1383.99 | 1114.35 | 2025-08-11 | 2025-11-25 | Partially Available | Mid-Level | Current | 10 | Resource allocation for Safety Inspector on project PROJ001
R0011 | PROJ002 | Project Manager | Project Manager - Team C | 150 | 22.9 | 20.2 | 88.2 | 3438.29 | 3044.62 | 2025-06-16 | 2025-11-04 | Overallocated | Junior | Expired | 8 | Resource allocation for Project Manager on project PROJ002
R0012 | PROJ002 | Site Supervisor | Site Supervisor - Team B | 120 | 43.3 | 39.8 | 92 | 5197.98 | 4703.91 | 2025-07-28 | 2025-12-06 | Partially Available | Expert | Expiring Soon | 9 | Resource allocation for Site Supervisor on project PROJ002
R0013 | PROJ002 | Structural Engineer | Structural Engineer - Team C | 140 | 17.5 | 15.7 | 90.1 | 2444.53 | 2288.77 | 2025-04-24 | 2025-12-23 | Available | Junior | Expiring Soon | 8 | Resource allocation for Structural Engineer on project PROJ002
R0014 | PROJ002 | MEP Engineer | MEP Engineer - Team B | 130 | 30.6 | 25.6 | 83.9 | 3973.23 | 3513.04 | 2025-06-06 | 2026-02-10 | Overallocated | Expert | Current | 8 | Resource allocation for MEP Engineer on project PROJ002
R0015 | PROJ002 | General Labor | General Labor - Team B | 35 | 291.1 | 222.6 | 76.5 | 10187.83 | 8518.04 | 2025-08-01 | 2025-12-14 | Overallocated | Expert | Expired | 10 | Resource allocation for General Labor on project PROJ002
R0016 | PROJ002 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 127 | 116.1 | 91.4 | 5713.04 | 5623.03 | 2025-08-20 | 2025-12-25 | Overallocated | Senior | Current | 7 | Resource allocation for Skilled Carpenter on project PROJ002
R0017 | PROJ002 | Electrician | Electrician - Team C | 55 | 107.9 | 88 | 81.6 | 5932.58 | 4871.72 | 2025-06-16 | 2025-10-20 | Available | Senior | Expired | 8 | Resource allocation for Electrician on project PROJ002
R0018 | PROJ002 | Plumber | Plumber - Team A | 50 | 84.5 | 73.9 | 87.4 | 4225.1 | 3610.38 | 2025-07-03 | 2025-11-08 | Partially Available | Senior | Current | 8 | Resource allocation for Plumber on project PROJ002
R0019 | PROJ002 | Heavy Equipment Operator | Heavy Equipment Operator - Team C | 60 | 69.6 | 51.6 | 74.1 | 4176.55 | 3238.16 | 2025-04-07 | 2025-12-24 | Overallocated | Expert | Expired | 7 | Resource allocation for Heavy Equipment Operator on project PROJ002
R0020 | PROJ002 | Safety Inspector | Safety Inspector - Team C | 80 | 14.4 | 13.4 | 93.3 | 1152.38 | 1089.66 | 2025-06-08 | 2025-12-01 | Overallocated | Junior | Expiring Soon | 7 | Resource allocation for Safety Inspector on project PROJ002
R0021 | PROJ003 | Project Manager | Project Manager - Team A | 150 | 33.3 | 29.3 | 88.1 | 4991.89 | 4518.53 | 2025-05-07 | 2025-11-09 | Overallocated | Mid-Level | Expiring Soon | 7 | Resource allocation for Project Manager on project PROJ003
R0022 | PROJ003 | Site Supervisor | Site Supervisor - Team B | 120 | 43.9 | 31 | 70.5 | 5272.53 | 3828.59 | 2025-03-25 | 2025-12-04 | Partially Available | Senior | Current | 7 | Resource allocation for Site Supervisor on project PROJ003
R0023 | PROJ003 | Structural Engineer | Structural Engineer - Team B | 140 | 23.6 | 22.3 | 94.4 | 3301.99 | 3025.5 | 2025-04-30 | 2025-11-18 | Partially Available | Senior | Current | 7 | Resource allocation for Structural Engineer on project PROJ003
R0024 | PROJ003 | MEP Engineer | MEP Engineer - Team C | 130 | 16.3 | 14.9 | 91.4 | 2118.36 | 2076.02 | 2025-05-05 | 2025-12-09 | Overallocated | Expert | Current | 8 | Resource allocation for MEP Engineer on project PROJ003
R0025 | PROJ003 | General Labor | General Labor - Team B | 35 | 210.7 | 164.6 | 78.1 | 7373.93 | 5935.94 | 2025-07-15 | 2025-11-04 | Overallocated | Junior | Expired | 7 | Resource allocation for General Labor on project PROJ003
R0026 | PROJ003 | Skilled Carpenter | Skilled Carpenter - Team C | 45 | 128.7 | 92.1 | 71.6 | 5791.57 | 4456.99 | 2025-08-04 | 2025-11-21 | Available | Junior | Current | 9 | Resource allocation for Skilled Carpenter on project PROJ003
R0027 | PROJ003 | Electrician | Electrician - Team A | 55 | 70.9 | 66.9 | 94.4 | 3897.44 | 3936.57 | 2025-06-26 | 2026-02-04 | Partially Available | Expert | Expired | 8 | Resource allocation for Electrician on project PROJ003
R0028 | PROJ003 | Plumber | Plumber - Team C | 50 | 44.2 | 38.1 | 86.3 | 2208.81 | 1853.79 | 2025-07-30 | 2025-11-26 | Overallocated | Junior | Expired | 8 | Resource allocation for Plumber on project PROJ003
R0029 | PROJ003 | Heavy Equipment Operator | Heavy Equipment Operator - Team A | 60 | 77.4 | 59.3 | 76.7 | 4642.02 | 3812.56 | 2025-05-07 | 2026-02-22 | Available | Senior | Expired | 9 | Resource allocation for Heavy Equipment Operator on project PROJ003
R0030 | PROJ003 | Safety Inspector | Safety Inspector - Team C | 80 | 19.2 | 13.7 | 71.4 | 1533.04 | 1153.72 | 2025-07-06 | 2025-12-27 | Available | Mid-Level | Expiring Soon | 10 | Resource allocation for Safety Inspector on project PROJ003
R0031 | PROJ004 | Project Manager | Project Manager - Team B | 150 | 42.6 | 32.3 | 75.9 | 6386.42 | 5093.27 | 2025-06-12 | 2026-01-13 | Overallocated | Expert | Current | 9 | Resource allocation for Project Manager on project PROJ004
R0032 | PROJ004 | Site Supervisor | Site Supervisor - Team A | 120 | 28.8 | 20.2 | 70 | 3454.01 | 2561.96 | 2025-07-11 | 2025-11-16 | Overallocated | Mid-Level | Expiring Soon | 10 | Resource allocation for Site Supervisor on project PROJ004
R0033 | PROJ004 | Structural Engineer | Structural Engineer - Team B | 140 | 11.2 | 8.5 | 76.3 | 1564.54 | 1178.19 | 2025-08-05 | 2025-10-21 | Overallocated | Junior | Current | 7 | Resource allocation for Structural Engineer on project PROJ004
R0034 | PROJ004 | MEP Engineer | MEP Engineer - Team A | 130 | 31.5 | 24.6 | 78 | 4097.95 | 3496.09 | 2025-04-10 | 2025-10-25 | Overallocated | Junior | Current | 10 | Resource allocation for MEP Engineer on project PROJ004
R0035 | PROJ004 | General Labor | General Labor - Team B | 35 | 203.3 | 162.2 | 79.8 | 7116.07 | 5468.54 | 2025-08-07 | 2026-02-19 | Overallocated | Senior | Current | 9 | Resource allocation for General Labor on project PROJ004
R0036 | PROJ004 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 148.2 | 132.2 | 89.2 | 6667.18 | 5844.14 | 2025-06-30 | 2026-01-03 | Available | Mid-Level | Expired | 8 | Resource allocation for Skilled Carpenter on project PROJ004
R0037 | PROJ004 | Electrician | Electrician - Team C | 55 | 104.2 | 87.3 | 83.8 | 5732.22 | 5024.62 | 2025-07-02 | 2026-03-02 | Partially Available | Mid-Level | Expiring Soon | 8 | Resource allocation for Electrician on project PROJ004
R0038 | PROJ004 | Plumber | Plumber - Team A | 50 | 62 | 54.7 | 88.2 | 3098.98 | 2678.81 | 2025-04-14 | 2025-12-19 | Overallocated | Mid-Level | Expiring Soon | 8 | Resource allocation for Plumber on project PROJ004
R0039 | PROJ004 | Heavy Equipment Operator | Heavy Equipment Operator - Team B | 60 | 48.1 | 42.8 | 89 | 2887.83 | 2503.7 | 2025-04-26 | 2026-01-22 | Overallocated | Mid-Level | Current | 9 | Resource allocation for Heavy Equipment Operator on project PROJ004
R0040 | PROJ004 | Safety Inspector | Safety Inspector - Team A | 80 | 20.5 | 16.1 | 78.3 | 1643.64 | 1232.44 | 2025-08-03 | 2025-10-26 | Overallocated | Senior | Expired | 7 | Resource allocation for Safety Inspector on project PROJ004
R0041 | PROJ005 | Project Manager | Project Manager - Team C | 150 | 22.1 | 20.6 | 93.4 | 3310.45 | 3230.14 | 2025-04-30 | 2026-01-14 | Partially Available | Expert | Expiring Soon | 7 | Resource allocation for Project Manager on project PROJ005
R0042 | PROJ005 | Site Supervisor | Site Supervisor - Team A | 120 | 41.7 | 31.9 | 76.5 | 5005.75 | 4051.12 | 2025-04-12 | 2026-02-24 | Overallocated | Senior | Expired | 8 | Resource allocation for Site Supervisor on project PROJ005
R0043 | PROJ005 | Structural Engineer | Structural Engineer - Team C | 140 | 20.5 | 18.8 | 91.9 | 2865.15 | 2827.15 | 2025-07-29 | 2026-01-05 | Overallocated | Expert | Current | 10 | Resource allocation for Structural Engineer on project PROJ005
R0044 | PROJ005 | MEP Engineer | MEP Engineer - Team C | 130 | 28.3 | 24.1 | 85.1 | 3678.95 | 3249.43 | 2025-05-22 | 2025-12-20 | Partially Available | Junior | Current | 8 | Resource allocation for MEP Engineer on project PROJ005
R0045 | PROJ005 | General Labor | General Labor - Team C | 35 | 299.3 | 230.3 | 76.9 | 10476.2 | 8154.7 | 2025-03-23 | 2026-02-17 | Available | Expert | Expiring Soon | 7 | Resource allocation for General Labor on project PROJ005
R0046 | PROJ005 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 116.3 | 109.5 | 94.2 | 5232.71 | 5147.71 | 2025-04-11 | 2026-01-21 | Partially Available | Mid-Level | Expiring Soon | 8 | Resource allocation for Skilled Carpenter on project PROJ005
R0047 | PROJ005 | Electrician | Electrician - Team C | 55 | 118 | 83.9 | 71 | 6492.18 | 5063.99 | 2025-03-27 | 2025-12-04 | Overallocated | Expert | Expiring Soon | 7 | Resource allocation for Electrician on project PROJ005
R0048 | PROJ005 | Plumber | Plumber - Team B | 50 | 92.4 | 72 | 77.9 | 4619.32 | 3836.55 | 2025-08-17 | 2025-11-21 | Overallocated | Senior | Current | 8 | Resource allocation for Plumber on project PROJ005
R0049 | PROJ005 | Heavy Equipment Operator | Heavy Equipment Operator - Team A | 60 | 44.3 | 37.6 | 84.9 | 2658.47 | 2442.76 | 2025-04-06 | 2025-11-28 | Partially Available | Junior | Current | 10 | Resource allocation for Heavy Equipment Operator on project PROJ005
R0050 | PROJ005 | Safety Inspector | Safety Inspector - Team B | 80 | 22.2 | 16.5 | 74.6 | 1774.5 | 1390.01 | 2025-06-02 | 2026-02-22 | Overallocated | Expert | Expired | 10 | Resource allocation for Safety Inspector on project PROJ005
R0051 | PROJ006 | Project Manager | Project Manager - Team C | 150 | 27.8 | 25.2 | 90.4 | 4175.44 | 3926.86 | 2025-03-31 | 2026-02-16 | Overallocated | Senior | Expired | 8 | Resource allocation for Project Manager on project PROJ006
R0052 | PROJ006 | Site Supervisor | Site Supervisor - Team B | 120 | 21.5 | 15.2 | 70.6 | 2582.8 | 1781.15 | 2025-04-26 | 2026-02-04 | Partially Available | Expert | Current | 8 | Resource allocation for Site Supervisor on project PROJ006
R0053 | PROJ006 | Structural Engineer | Structural Engineer - Team B | 140 | 22.3 | 16.6 | 74.3 | 3125.71 | 2242.59 | 2025-05-25 | 2025-12-04 | Available | Junior | Expired | 7 | Resource allocation for Structural Engineer on project PROJ006
R0054 | PROJ006 | MEP Engineer | MEP Engineer - Team A | 130 | 30.3 | 28.2 | 93.2 | 3933.41 | 4032.27 | 2025-03-26 | 2026-01-28 | Overallocated | Senior | Expiring Soon | 10 | Resource allocation for MEP Engineer on project PROJ006
R0055 | PROJ006 | General Labor | General Labor - Team A | 35 | 293 | 277.5 | 94.7 | 10256.62 | 10513.64 | 2025-06-11 | 2026-01-28 | Partially Available | Expert | Current | 7 | Resource allocation for General Labor on project PROJ006
R0056 | PROJ006 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 137.4 | 128.6 | 93.6 | 6184.83 | 5516.85 | 2025-05-26 | 2026-02-26 | Overallocated | Expert | Expired | 9 | Resource allocation for Skilled Carpenter on project PROJ006
R0057 | PROJ006 | Electrician | Electrician - Team B | 55 | 113 | 101.4 | 89.7 | 6213.11 | 5764.5 | 2025-07-28 | 2025-11-30 | Available | Mid-Level | Expiring Soon | 10 | Resource allocation for Electrician on project PROJ006
R0058 | PROJ006 | Plumber | Plumber - Team C | 50 | 52.7 | 49 | 93 | 2634.02 | 2488.53 | 2025-05-28 | 2026-02-28 | Available | Expert | Expiring Soon | 8 | Resource allocation for Plumber on project PROJ006
R0059 | PROJ006 | Heavy Equipment Operator | Heavy Equipment Operator - Team C | 60 | 88.9 | 84.4 | 95 | 5334.18 | 5284.81 | 2025-05-17 | 2025-12-17 | Available | Senior | Expiring Soon | 9 | Resource allocation for Heavy Equipment Operator on project PROJ006
R0060 | PROJ006 | Safety Inspector | Safety Inspector - Team B | 80 | 23.9 | 18.8 | 78.5 | 1914.5 | 1521.19 | 2025-06-11 | 2026-01-08 | Available | Mid-Level | Expired | 8 | Resource allocation for Safety Inspector on project PROJ006
R0061 | PROJ007 | Project Manager | Project Manager - Team C | 150 | 25.5 | 21 | 82.3 | 3828.05 | 3426.52 | 2025-07-19 | 2026-01-12 | Overallocated | Expert | Current | 7 | Resource allocation for Project Manager on project PROJ007
R0062 | PROJ007 | Site Supervisor | Site Supervisor - Team A | 120 | 28 | 25 | 89.6 | 3355.5 | 3123.74 | 2025-06-08 | 2026-01-18 | Available | Mid-Level | Current | 7 | Resource allocation for Site Supervisor on project PROJ007
R0063 | PROJ007 | Structural Engineer | Structural Engineer - Team B | 140 | 16.5 | 13.8 | 83.4 | 2315.63 | 1887.55 | 2025-03-27 | 2026-03-14 | Overallocated | Junior | Expiring Soon | 10 | Resource allocation for Structural Engineer on project PROJ007
R0064 | PROJ007 | MEP Engineer | MEP Engineer - Team A | 130 | 25.3 | 18 | 71.1 | 3292.09 | 2514.83 | 2025-05-06 | 2025-12-05 | Overallocated | Junior | Expiring Soon | 8 | Resource allocation for MEP Engineer on project PROJ007
R0065 | PROJ007 | General Labor | General Labor - Team B | 35 | 231.7 | 220 | 95 | 8110.38 | 7468.03 | 2025-03-30 | 2026-01-08 | Partially Available | Expert | Expired | 9 | Resource allocation for General Labor on project PROJ007
R0066 | PROJ007 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 137.5 | 105.6 | 76.8 | 6188.67 | 4693.91 | 2025-06-15 | 2026-03-17 | Available | Expert | Current | 8 | Resource allocation for Skilled Carpenter on project PROJ007
R0067 | PROJ007 | Electrician | Electrician - Team B | 55 | 89.9 | 82.7 | 92 | 4942.59 | 4728.64 | 2025-03-23 | 2026-02-28 | Available | Junior | Expired | 8 | Resource allocation for Electrician on project PROJ007
R0068 | PROJ007 | Plumber | Plumber - Team B | 50 | 86 | 72.8 | 84.6 | 4301.14 | 3947.79 | 2025-05-10 | 2025-12-17 | Available | Senior | Expiring Soon | 8 | Resource allocation for Plumber on project PROJ007
R0069 | PROJ007 | Heavy Equipment Operator | Heavy Equipment Operator - Team A | 60 | 52.9 | 46.3 | 87.6 | 3171.35 | 2907.17 | 2025-04-15 | 2026-01-24 | Available | Junior | Expired | 9 | Resource allocation for Heavy Equipment Operator on project PROJ007
R0070 | PROJ007 | Safety Inspector | Safety Inspector - Team C | 80 | 11 | 8.1 | 73.2 | 882.06 | 670.34 | 2025-05-28 | 2026-03-16 | Overallocated | Expert | Expired | 7 | Resource allocation for Safety Inspector on project PROJ007

## Summary
Metric | Value
Total Projects | 7
Total Budget | $178,000,000
Active Projects | 5
Avg Progress | 89.0%
Tasks with Delays | 19
Over Budget Items | 1
Total Resources | 70
Data Generated | 2025-09-19 12:36:21