## Sheet1
Resource_ID | Project_ID | Resource_Type | Resource_Name | Hourly_Rate | Allocated_Hours_Weekly | Utilized_Hours_Weekly | Efficiency_Percent | Allocated_Cost_Weekly | Actual_Cost_Weekly | Start_Date | End_Date | Availability_Status | Skill_Level | Certification_Status | Performance_Rating | Notes
R0001 | PROJ001 | Project Manager | Project Manager - Team A | 150 | 37 | 26.1 | 70.5 | 5549.63 | 4060.45 | 2025-08-19 | 2025-11-23 | Overallocated | Junior | Current | 10 | Resource allocation for Project Manager on project PROJ001
R0002 | PROJ001 | Site Supervisor | Site Supervisor - Team A | 120 | 28.4 | 21.4 | 75.2 | 3409.26 | 2565.57 | 2025-07-14 | 2025-12-16 | Available | Senior | Expiring Soon | 9 | Resource allocation for Site Supervisor on project PROJ001
R0003 | PROJ001 | Structural Engineer | Structural Engineer - Team B | 140 | 17.3 | 13.2 | 76.3 | 2426.65 | 1951.23 | 2025-08-01 | 2025-12-13 | Overallocated | Mid-Level | Current | 8 | Resource allocation for Structural Engineer on project PROJ001
R0004 | PROJ001 | MEP Engineer | MEP Engineer - Team A | 130 | 32.1 | 26.1 | 81.2 | 4169.03 | 3700.08 | 2025-08-02 | 2025-11-23 | Available | Junior | Expiring Soon | 8 | Resource allocation for MEP Engineer on project PROJ001
R0005 | PROJ001 | General Labor | General Labor - Team C | 35 | 314.9 | 258.2 | 82 | 11022.26 | 9759.9 | 2025-07-07 | 2026-01-20 | Partially Available | Mid-Level | Expiring Soon | 8 | Resource allocation for General Labor on project PROJ001
R0006 | PROJ001 | Skilled Carpenter | Skilled Carpenter - Team C | 45 | 132.3 | 93.6 | 70.7 | 5954.21 | 4523.37 | 2025-06-23 | 2025-12-05 | Available | Senior | Expiring Soon | 10 | Resource allocation for Skilled Carpenter on project PROJ001
R0007 | PROJ001 | Electrician | Electrician - Team A | 55 | 128.9 | 114.7 | 89 | 7090.3 | 6787.9 | 2025-04-11 | 2025-12-01 | Partially Available | Junior | Expiring Soon | 7 | Resource allocation for Electrician on project PROJ001
R0008 | PROJ001 | Plumber | Plumber - Team B | 50 | 69.2 | 51.1 | 73.9 | 3457.54 | 2588.52 | 2025-05-19 | 2026-01-15 | Partially Available | Junior | Expired | 7 | Resource allocation for Plumber on project PROJ001
R0009 | PROJ001 | Heavy Equipment Operator | Heavy Equipment Operator - Team B | 60 | 89.2 | 67 | 75.1 | 5350.84 | 4016.83 | 2025-05-09 | 2025-12-15 | Overallocated | Senior | Current | 9 | Resource allocation for Heavy Equipment Operator on project PROJ001
R0010 | PROJ001 | Safety Inspector | Safety Inspector - Team B | 80 | 17.3 | 12.9 | 74.4 | 1383.99 | 1114.35 | 2025-08-11 | 2025-11-25 | Partially Available | Mid-Level | Current | 10 | Resource allocation for Safety Inspector on project PROJ001
R0011 | PROJ002 | Project Manager | Project Manager - Team C | 150 | 22.9 | 20.2 | 88.2 | 3438.29 | 3044.62 | 2025-06-16 | 2025-11-04 | Overallocated | Junior | Expired | 8 | Resource allocation for Project Manager on project PROJ002
R0012 | PROJ002 | Site Supervisor | Site Supervisor - Team B | 120 | 43.3 | 39.8 | 92 | 5197.98 | 4703.91 | 2025-07-28 | 2025-12-06 | Partially Available | Expert | Expiring Soon | 9 | Resource allocation for Site Supervisor on project PROJ002
R0013 | PROJ002 | Structural Engineer | Structural Engineer - Team C | 140 | 17.5 | 15.7 | 90.1 | 2444.53 | 2288.77 | 2025-04-24 | 2025-12-23 | Available | Junior | Expiring Soon | 8 | Resource allocation for Structural Engineer on project PROJ002
R0014 | PROJ002 | MEP Engineer | MEP Engineer - Team B | 130 | 30.6 | 25.6 | 83.9 | 3973.23 | 3513.04 | 2025-06-06 | 2026-02-10 | Overallocated | Expert | Current | 8 | Resource allocation for MEP Engineer on project PROJ002
R0015 | PROJ002 | General Labor | General Labor - Team B | 35 | 291.1 | 222.6 | 76.5 | 10187.83 | 8518.04 | 2025-08-01 | 2025-12-14 | Overallocated | Expert | Expired | 10 | Resource allocation for General Labor on project PROJ002
R0016 | PROJ002 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 127 | 116.1 | 91.4 | 5713.04 | 5623.03 | 2025-08-20 | 2025-12-25 | Overallocated | Senior | Current | 7 | Resource allocation for Skilled Carpenter on project PROJ002
R0017 | PROJ002 | Electrician | Electrician - Team C | 55 | 107.9 | 88 | 81.6 | 5932.58 | 4871.72 | 2025-06-16 | 2025-10-20 | Available | Senior | Expired | 8 | Resource allocation for Electrician on project PROJ002
R0018 | PROJ002 | Plumber | Plumber - Team A | 50 | 84.5 | 73.9 | 87.4 | 4225.1 | 3610.38 | 2025-07-03 | 2025-11-08 | Partially Available | Senior | Current | 8 | Resource allocation for Plumber on project PROJ002
R0019 | PROJ002 | Heavy Equipment Operator | Heavy Equipment Operator - Team C | 60 | 69.6 | 51.6 | 74.1 | 4176.55 | 3238.16 | 2025-04-07 | 2025-12-24 | Overallocated | Expert | Expired | 7 | Resource allocation for Heavy Equipment Operator on project PROJ002
R0020 | PROJ002 | Safety Inspector | Safety Inspector - Team C | 80 | 14.4 | 13.4 | 93.3 | 1152.38 | 1089.66 | 2025-06-08 | 2025-12-01 | Overallocated | Junior | Expiring Soon | 7 | Resource allocation for Safety Inspector on project PROJ002
R0021 | PROJ003 | Project Manager | Project Manager - Team A | 150 | 33.3 | 29.3 | 88.1 | 4991.89 | 4518.53 | 2025-05-07 | 2025-11-09 | Overallocated | Mid-Level | Expiring Soon | 7 | Resource allocation for Project Manager on project PROJ003
R0022 | PROJ003 | Site Supervisor | Site Supervisor - Team B | 120 | 43.9 | 31 | 70.5 | 5272.53 | 3828.59 | 2025-03-25 | 2025-12-04 | Partially Available | Senior | Current | 7 | Resource allocation for Site Supervisor on project PROJ003
R0023 | PROJ003 | Structural Engineer | Structural Engineer - Team B | 140 | 23.6 | 22.3 | 94.4 | 3301.99 | 3025.5 | 2025-04-30 | 2025-11-18 | Partially Available | Senior | Current | 7 | Resource allocation for Structural Engineer on project PROJ003
R0024 | PROJ003 | MEP Engineer | MEP Engineer - Team C | 130 | 16.3 | 14.9 | 91.4 | 2118.36 | 2076.02 | 2025-05-05 | 2025-12-09 | Overallocated | Expert | Current | 8 | Resource allocation for MEP Engineer on project PROJ003
R0025 | PROJ003 | General Labor | General Labor - Team B | 35 | 210.7 | 164.6 | 78.1 | 7373.93 | 5935.94 | 2025-07-15 | 2025-11-04 | Overallocated | Junior | Expired | 7 | Resource allocation for General Labor on project PROJ003
R0026 | PROJ003 | Skilled Carpenter | Skilled Carpenter - Team C | 45 | 128.7 | 92.1 | 71.6 | 5791.57 | 4456.99 | 2025-08-04 | 2025-11-21 | Available | Junior | Current | 9 | Resource allocation for Skilled Carpenter on project PROJ003
R0027 | PROJ003 | Electrician | Electrician - Team A | 55 | 70.9 | 66.9 | 94.4 | 3897.44 | 3936.57 | 2025-06-26 | 2026-02-04 | Partially Available | Expert | Expired | 8 | Resource allocation for Electrician on project PROJ003
R0028 | PROJ003 | Plumber | Plumber - Team C | 50 | 44.2 | 38.1 | 86.3 | 2208.81 | 1853.79 | 2025-07-30 | 2025-11-26 | Overallocated | Junior | Expired | 8 | Resource allocation for Plumber on project PROJ003
R0029 | PROJ003 | Heavy Equipment Operator | Heavy Equipment Operator - Team A | 60 | 77.4 | 59.3 | 76.7 | 4642.02 | 3812.56 | 2025-05-07 | 2026-02-22 | Available | Senior | Expired | 9 | Resource allocation for Heavy Equipment Operator on project PROJ003
R0030 | PROJ003 | Safety Inspector | Safety Inspector - Team C | 80 | 19.2 | 13.7 | 71.4 | 1533.04 | 1153.72 | 2025-07-06 | 2025-12-27 | Available | Mid-Level | Expiring Soon | 10 | Resource allocation for Safety Inspector on project PROJ003
R0031 | PROJ004 | Project Manager | Project Manager - Team B | 150 | 42.6 | 32.3 | 75.9 | 6386.42 | 5093.27 | 2025-06-12 | 2026-01-13 | Overallocated | Expert | Current | 9 | Resource allocation for Project Manager on project PROJ004
R0032 | PROJ004 | Site Supervisor | Site Supervisor - Team A | 120 | 28.8 | 20.2 | 70 | 3454.01 | 2561.96 | 2025-07-11 | 2025-11-16 | Overallocated | Mid-Level | Expiring Soon | 10 | Resource allocation for Site Supervisor on project PROJ004
R0033 | PROJ004 | Structural Engineer | Structural Engineer - Team B | 140 | 11.2 | 8.5 | 76.3 | 1564.54 | 1178.19 | 2025-08-05 | 2025-10-21 | Overallocated | Junior | Current | 7 | Resource allocation for Structural Engineer on project PROJ004
R0034 | PROJ004 | MEP Engineer | MEP Engineer - Team A | 130 | 31.5 | 24.6 | 78 | 4097.95 | 3496.09 | 2025-04-10 | 2025-10-25 | Overallocated | Junior | Current | 10 | Resource allocation for MEP Engineer on project PROJ004
R0035 | PROJ004 | General Labor | General Labor - Team B | 35 | 203.3 | 162.2 | 79.8 | 7116.07 | 5468.54 | 2025-08-07 | 2026-02-19 | Overallocated | Senior | Current | 9 | Resource allocation for General Labor on project PROJ004
R0036 | PROJ004 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 148.2 | 132.2 | 89.2 | 6667.18 | 5844.14 | 2025-06-30 | 2026-01-03 | Available | Mid-Level | Expired | 8 | Resource allocation for Skilled Carpenter on project PROJ004
R0037 | PROJ004 | Electrician | Electrician - Team C | 55 | 104.2 | 87.3 | 83.8 | 5732.22 | 5024.62 | 2025-07-02 | 2026-03-02 | Partially Available | Mid-Level | Expiring Soon | 8 | Resource allocation for Electrician on project PROJ004
R0038 | PROJ004 | Plumber | Plumber - Team A | 50 | 62 | 54.7 | 88.2 | 3098.98 | 2678.81 | 2025-04-14 | 2025-12-19 | Overallocated | Mid-Level | Expiring Soon | 8 | Resource allocation for Plumber on project PROJ004
R0039 | PROJ004 | Heavy Equipment Operator | Heavy Equipment Operator - Team B | 60 | 48.1 | 42.8 | 89 | 2887.83 | 2503.7 | 2025-04-26 | 2026-01-22 | Overallocated | Mid-Level | Current | 9 | Resource allocation for Heavy Equipment Operator on project PROJ004
R0040 | PROJ004 | Safety Inspector | Safety Inspector - Team A | 80 | 20.5 | 16.1 | 78.3 | 1643.64 | 1232.44 | 2025-08-03 | 2025-10-26 | Overallocated | Senior | Expired | 7 | Resource allocation for Safety Inspector on project PROJ004
R0041 | PROJ005 | Project Manager | Project Manager - Team C | 150 | 22.1 | 20.6 | 93.4 | 3310.45 | 3230.14 | 2025-04-30 | 2026-01-14 | Partially Available | Expert | Expiring Soon | 7 | Resource allocation for Project Manager on project PROJ005
R0042 | PROJ005 | Site Supervisor | Site Supervisor - Team A | 120 | 41.7 | 31.9 | 76.5 | 5005.75 | 4051.12 | 2025-04-12 | 2026-02-24 | Overallocated | Senior | Expired | 8 | Resource allocation for Site Supervisor on project PROJ005
R0043 | PROJ005 | Structural Engineer | Structural Engineer - Team C | 140 | 20.5 | 18.8 | 91.9 | 2865.15 | 2827.15 | 2025-07-29 | 2026-01-05 | Overallocated | Expert | Current | 10 | Resource allocation for Structural Engineer on project PROJ005
R0044 | PROJ005 | MEP Engineer | MEP Engineer - Team C | 130 | 28.3 | 24.1 | 85.1 | 3678.95 | 3249.43 | 2025-05-22 | 2025-12-20 | Partially Available | Junior | Current | 8 | Resource allocation for MEP Engineer on project PROJ005
R0045 | PROJ005 | General Labor | General Labor - Team C | 35 | 299.3 | 230.3 | 76.9 | 10476.2 | 8154.7 | 2025-03-23 | 2026-02-17 | Available | Expert | Expiring Soon | 7 | Resource allocation for General Labor on project PROJ005
R0046 | PROJ005 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 116.3 | 109.5 | 94.2 | 5232.71 | 5147.71 | 2025-04-11 | 2026-01-21 | Partially Available | Mid-Level | Expiring Soon | 8 | Resource allocation for Skilled Carpenter on project PROJ005
R0047 | PROJ005 | Electrician | Electrician - Team C | 55 | 118 | 83.9 | 71 | 6492.18 | 5063.99 | 2025-03-27 | 2025-12-04 | Overallocated | Expert | Expiring Soon | 7 | Resource allocation for Electrician on project PROJ005
R0048 | PROJ005 | Plumber | Plumber - Team B | 50 | 92.4 | 72 | 77.9 | 4619.32 | 3836.55 | 2025-08-17 | 2025-11-21 | Overallocated | Senior | Current | 8 | Resource allocation for Plumber on project PROJ005
R0049 | PROJ005 | Heavy Equipment Operator | Heavy Equipment Operator - Team A | 60 | 44.3 | 37.6 | 84.9 | 2658.47 | 2442.76 | 2025-04-06 | 2025-11-28 | Partially Available | Junior | Current | 10 | Resource allocation for Heavy Equipment Operator on project PROJ005
R0050 | PROJ005 | Safety Inspector | Safety Inspector - Team B | 80 | 22.2 | 16.5 | 74.6 | 1774.5 | 1390.01 | 2025-06-02 | 2026-02-22 | Overallocated | Expert | Expired | 10 | Resource allocation for Safety Inspector on project PROJ005
R0051 | PROJ006 | Project Manager | Project Manager - Team C | 150 | 27.8 | 25.2 | 90.4 | 4175.44 | 3926.86 | 2025-03-31 | 2026-02-16 | Overallocated | Senior | Expired | 8 | Resource allocation for Project Manager on project PROJ006
R0052 | PROJ006 | Site Supervisor | Site Supervisor - Team B | 120 | 21.5 | 15.2 | 70.6 | 2582.8 | 1781.15 | 2025-04-26 | 2026-02-04 | Partially Available | Expert | Current | 8 | Resource allocation for Site Supervisor on project PROJ006
R0053 | PROJ006 | Structural Engineer | Structural Engineer - Team B | 140 | 22.3 | 16.6 | 74.3 | 3125.71 | 2242.59 | 2025-05-25 | 2025-12-04 | Available | Junior | Expired | 7 | Resource allocation for Structural Engineer on project PROJ006
R0054 | PROJ006 | MEP Engineer | MEP Engineer - Team A | 130 | 30.3 | 28.2 | 93.2 | 3933.41 | 4032.27 | 2025-03-26 | 2026-01-28 | Overallocated | Senior | Expiring Soon | 10 | Resource allocation for MEP Engineer on project PROJ006
R0055 | PROJ006 | General Labor | General Labor - Team A | 35 | 293 | 277.5 | 94.7 | 10256.62 | 10513.64 | 2025-06-11 | 2026-01-28 | Partially Available | Expert | Current | 7 | Resource allocation for General Labor on project PROJ006
R0056 | PROJ006 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 137.4 | 128.6 | 93.6 | 6184.83 | 5516.85 | 2025-05-26 | 2026-02-26 | Overallocated | Expert | Expired | 9 | Resource allocation for Skilled Carpenter on project PROJ006
R0057 | PROJ006 | Electrician | Electrician - Team B | 55 | 113 | 101.4 | 89.7 | 6213.11 | 5764.5 | 2025-07-28 | 2025-11-30 | Available | Mid-Level | Expiring Soon | 10 | Resource allocation for Electrician on project PROJ006
R0058 | PROJ006 | Plumber | Plumber - Team C | 50 | 52.7 | 49 | 93 | 2634.02 | 2488.53 | 2025-05-28 | 2026-02-28 | Available | Expert | Expiring Soon | 8 | Resource allocation for Plumber on project PROJ006
R0059 | PROJ006 | Heavy Equipment Operator | Heavy Equipment Operator - Team C | 60 | 88.9 | 84.4 | 95 | 5334.18 | 5284.81 | 2025-05-17 | 2025-12-17 | Available | Senior | Expiring Soon | 9 | Resource allocation for Heavy Equipment Operator on project PROJ006
R0060 | PROJ006 | Safety Inspector | Safety Inspector - Team B | 80 | 23.9 | 18.8 | 78.5 | 1914.5 | 1521.19 | 2025-06-11 | 2026-01-08 | Available | Mid-Level | Expired | 8 | Resource allocation for Safety Inspector on project PROJ006
R0061 | PROJ007 | Project Manager | Project Manager - Team C | 150 | 25.5 | 21 | 82.3 | 3828.05 | 3426.52 | 2025-07-19 | 2026-01-12 | Overallocated | Expert | Current | 7 | Resource allocation for Project Manager on project PROJ007
R0062 | PROJ007 | Site Supervisor | Site Supervisor - Team A | 120 | 28 | 25 | 89.6 | 3355.5 | 3123.74 | 2025-06-08 | 2026-01-18 | Available | Mid-Level | Current | 7 | Resource allocation for Site Supervisor on project PROJ007
R0063 | PROJ007 | Structural Engineer | Structural Engineer - Team B | 140 | 16.5 | 13.8 | 83.4 | 2315.63 | 1887.55 | 2025-03-27 | 2026-03-14 | Overallocated | Junior | Expiring Soon | 10 | Resource allocation for Structural Engineer on project PROJ007
R0064 | PROJ007 | MEP Engineer | MEP Engineer - Team A | 130 | 25.3 | 18 | 71.1 | 3292.09 | 2514.83 | 2025-05-06 | 2025-12-05 | Overallocated | Junior | Expiring Soon | 8 | Resource allocation for MEP Engineer on project PROJ007
R0065 | PROJ007 | General Labor | General Labor - Team B | 35 | 231.7 | 220 | 95 | 8110.38 | 7468.03 | 2025-03-30 | 2026-01-08 | Partially Available | Expert | Expired | 9 | Resource allocation for General Labor on project PROJ007
R0066 | PROJ007 | Skilled Carpenter | Skilled Carpenter - Team A | 45 | 137.5 | 105.6 | 76.8 | 6188.67 | 4693.91 | 2025-06-15 | 2026-03-17 | Available | Expert | Current | 8 | Resource allocation for Skilled Carpenter on project PROJ007
R0067 | PROJ007 | Electrician | Electrician - Team B | 55 | 89.9 | 82.7 | 92 | 4942.59 | 4728.64 | 2025-03-23 | 2026-02-28 | Available | Junior | Expired | 8 | Resource allocation for Electrician on project PROJ007
R0068 | PROJ007 | Plumber | Plumber - Team B | 50 | 86 | 72.8 | 84.6 | 4301.14 | 3947.79 | 2025-05-10 | 2025-12-17 | Available | Senior | Expiring Soon | 8 | Resource allocation for Plumber on project PROJ007
R0069 | PROJ007 | Heavy Equipment Operator | Heavy Equipment Operator - Team A | 60 | 52.9 | 46.3 | 87.6 | 3171.35 | 2907.17 | 2025-04-15 | 2026-01-24 | Available | Junior | Expired | 9 | Resource allocation for Heavy Equipment Operator on project PROJ007
R0070 | PROJ007 | Safety Inspector | Safety Inspector - Team C | 80 | 11 | 8.1 | 73.2 | 882.06 | 670.34 | 2025-05-28 | 2026-03-16 | Overallocated | Expert | Expired | 7 | Resource allocation for Safety Inspector on project PROJ007